## Gantt
Gantt, Oct 1 to Dec 12, 2026: generated by tools/make_gantt.py on 2026-10-30 from 181dd9d; today = 2026-10-30 (red column)
Legend: | ◆ milestone; red border = today; 'inferred' in the Dates column marks a derived date; +/- at the left folds a track or phase | [8 empty] | done | [8 empty] | in progress | [8 empty] | planned | [8 empty] | blocked
[9 empty] | October 2026 | [30 empty] | November 2026 | [29 empty] | December 2026
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
ID | Task | Status | Owner | Start | End / due | Dates (basis) | Depends on | Source | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
Milestones | Gate 1 10-25; Handoff C 10-30; Handoff B 11-03; Gate 2 11-08; Gate 3 11-22 | bar: October 2026 25; October 2026 30; November 2026 3; November 2026 8; November 2026 22
Setup and the progress round
The progress round (3 of 3 done)
P1 | Harness: client, puzzle generator, parser, keyword detector; difficulty ladder; Test 1 (24 puzzles × 6 models) | done | Ritik | 2026-10-01 | 2026-10-02 | start: OVERVIEW; end: OVERVIEW |  | OVERVIEW | bar: October 2026 1 to October 2026 2
P2 | Progress run: Test 2, Experiment A (reviewer demo), truncation sweep, timing. Every prompt and reply saved fr… | done | Ritik | 2026-10-04 | 2026-10-04 | start: OVERVIEW; end: OVERVIEW |  | OVERVIEW | bar: October 2026 4
P3 | Scope update (adapters, budget guard, real tool calls, Track A/B/C scaffolds); demo app | done | Ritik | 2026-10-04 | 2026-10-06 | start: OVERVIEW; end: OVERVIEW |  | OVERVIEW | bar: October 2026 4 to October 2026 6
Track A: explain and fix
Other (1 of 1 done)
A27 | Olmo 3 32B identity (3 vs 3.1) on Voyager | done | Ritik | 2026-10-04 | 2026-10-28 | start: TODO From; end: TODO status |  | TODO | bar: October 2026 4 to October 2026 28
Steps 1–10 (19 of 19 done)
Step 1 | Step 1: Voyager capabilities | done | Ritik | 2026-10-21 | 2026-10-21 | start: OVERVIEW; end: OVERVIEW |  | OVERVIEW | bar: October 2026 21
Step 2 | Step 2: the pinned format | done | Ritik | 2026-10-21 | 2026-10-21 | start: OVERVIEW; end: OVERVIEW |  | OVERVIEW | bar: October 2026 21
Step 2b | Step 2b: the base model in the pinned format | done | Ritik | 2026-10-21 | 2026-10-22 | start: OVERVIEW; end: OVERVIEW |  | OVERVIEW | bar: October 2026 21 to October 2026 22
Step 3 | Step 3: takeover curves | done | Ritik | 2026-10-22 | 2026-10-24 | start: OVERVIEW; end: OVERVIEW |  | OVERVIEW | bar: October 2026 22 to October 2026 24
Step 4 | Step 4: deleting the reasoning's mentions | done | Ritik | 2026-10-24 | 2026-10-24 | start: OVERVIEW; end: OVERVIEW |  | OVERVIEW | bar: October 2026 24
Step 5 | Step 5: the dataset rules | done | Ritik | 2026-10-24 | 2026-10-24 | start: OVERVIEW; end: OVERVIEW |  | OVERVIEW | bar: October 2026 24
Steps 6–7 | Steps 6–7: training data | done | Ritik | 2026-10-24 | 2026-10-27 | start: OVERVIEW; end: OVERVIEW |  | OVERVIEW | bar: October 2026 24 to October 2026 27
Step 8 | Step 8: the checkpoint check | done | Ritik | 2026-10-26 | 2026-10-26 | start: OVERVIEW; end: OVERVIEW |  | OVERVIEW | bar: October 2026 26
Step 9 | Step 9: attention to the hint | done | Ritik | 2026-10-26 | 2026-10-27 | start: OVERVIEW; end: OVERVIEW |  | OVERVIEW | bar: October 2026 26 to October 2026 27
Step 10 | Step 10: activation patching | done | Ritik | 2026-10-26 | 2026-10-26 | start: OVERVIEW; end: OVERVIEW |  | OVERVIEW | bar: October 2026 26
A1 | Steps 6–7 to 240 kept questions (run_steps67.py --kept 240 --checkpoint 100) | done | Ritik | 2026-10-25 | 2026-10-27 | start: TODO From; end: TODO status |  | TODO | bar: October 2026 25 to October 2026 27
A2 | The checkpoint report at 100 kept | done | Ritik | 2026-10-25 | 2026-10-26 | start: TODO From; end: TODO status |  | TODO | bar: October 2026 25 to October 2026 26
A3 | Final Steps 6–7 counts and the final-count log | done | Ritik | 2026-10-27 | 2026-10-27 | start: TODO From; end: the session log it names |  | TODO | bar: October 2026 27
A4 | Assemble train / validation (--assemble): 10% no-hint, "neither" dropped if under 10%, counts | done | Ritik | 2026-10-25 | 2026-10-27 | start: TODO From; end: TODO From (no done date) (inferred) |  | TODO | bar: October 2026 25 to October 2026 27
A5 | Export the final Steps 6–7 summaries | done | Ritik | 2026-10-26 | 2026-10-27 | start: TODO From; end: commit 56e2894 (inferred) |  | TODO | bar: October 2026 26 to October 2026 27
A22 | Figure #1: the pinned panel (Step 2b per channel) | done | Ritik | 2026-10-26 | 2026-10-27 | start: TODO From; end: TODO status |  | TODO | bar: October 2026 26 to October 2026 27
A23 | Figure #4: deletion vs control vs unedited | done | Ritik | 2026-10-26 | 2026-10-27 | start: TODO From; end: TODO status |  | TODO | bar: October 2026 26 to October 2026 27
A25 | Record Step 9's matched onsets | done | Ritik | 2026-10-27 | 2026-10-27 | start: TODO From; end: commit 07999f7 (inferred) |  | TODO | bar: October 2026 27
A26 | Copy Sol's original step9_followup.json to results/trackA/gpu/original/step9_followup_sol.json (gitignored) | done | Ritik | 2026-10-27 | 2026-10-27 | start: TODO From; end: TODO From (no done date) (inferred) |  | TODO | bar: October 2026 27
Steps 11–13: code and Sol kit (8 of 8 done)
A8 | Step 11 train.py: LoRA only, tags only, both; 32,768 tokens, chunked loss, gradient checkpointing, checkpoint after each epoch and resume; validation loss per… | done | Ritik | 2026-10-21 | 2026-10-27 | start: TODO From; end: commit f52a5ef (inferred) |  | TODO | bar: October 2026 21 to October 2026 27
A9 | Step 12 generation: tagged decoding loop, and the vLLM path (tags_vllm.py, equal on a tiny model on CPU) | done | Ritik | 2026-10-21 | 2026-10-27 | start: TODO From; end: commit f2a9c4f (inferred) |  | TODO | bar: October 2026 21 to October 2026 27
A10 | Step 13 eval.py: hint following, no-hint accuracy, mention, hiding check, false-disclosure check; X of Y, clustered bootstrap | done | Ritik | 2026-10-21 | 2026-10-27 | start: TODO From; end: commit f85f100 (inferred) |  | TODO | bar: October 2026 21 to October 2026 27
A11 | Sol job scripts for Steps 11–13 in the kit: account guard, checkpoint/resume; CPU tests | done | Ritik | 2026-10-25 | 2026-10-27 | start: TODO From; end: commit 9256acc (inferred) |  | TODO | bar: October 2026 25 to October 2026 27
A12 | Sol kit QoS checks (Oct 27): one config file of accounts, partitions, QoS and limits (only listed accounts allowed; today the course account); each job's limit… | done | Ritik | 2026-10-27 | 2026-10-27 | start: TODO From; end: commit 1608665 (inferred) |  | TODO | bar: October 2026 27
A24 | Sol scripts call /scratch/ragarw68/envs/olmo/bin/python by full path | done | Ritik | 2026-10-27 | 2026-10-27 | start: TODO From; end: commit 39f8534 (inferred) |  | TODO | bar: October 2026 27
A34 | vLLM's start failure on Sol (S2 66878660, Qwen3-8B 66879362: warmup_kernels in compile_or_warm_up_model): the root-cause line from the server logs (command in… | done | Ritik | 2026-10-29 | 2026-10-29 | start: TODO From; end: TODO status |  | TODO | bar: October 2026 29
A35 | Sol jobs, safe to run together and quick to fail (Oct 29): every job starts with finetune/gpu/import_check.py (torch, transformers with AutoTokenizer, tokenize… | done | Ritik | 2026-10-29 | 2026-10-29 | start: TODO From; end: commit ad7ce06 (inferred) |  | TODO | bar: October 2026 29
Training (S1–S6) (2 of 4 done)
A13 | First Sol jobs: setup_vllm (envs/olmo-vllm), S1 the timing run, S2 the vLLM check | in progress | Ritik | 2026-10-25 | 2026-11-20 | start: TODO From; end: PLAN: all evaluation done by (inferred) | Ritik submits | TODO | bar: October 2026 25 to November 2026 20
A15 | Train the versions (S3–S6) in batch 2: lora and tags at once, lora_tags after lora, lora_attn3 after tags (afterany); rank 16, LoRA 2e-4, tag table 1e-3, 2 epo… | done | Ritik | 2026-10-28 | 2026-10-28 | start: set to the done date (inferred); end: TODO status | A4, A13 (S1) | TODO | bar: October 2026 28
A19 | Fourth version (S6, E6): LoRA on the attention of layers 15, 19, 23 only; included, scheduled last, dropped if E1–E5 aren't done by Nov 9 | planned | Ritik | 2026-10-26 | 2026-11-09 | start: TODO From; end: TODO row | A16 | TODO | bar: October 2026 30 to November 2026 9
A20 | Training settings | done | Ritik | 2026-10-27 | 2026-10-27 | start: set to the done date (inferred); end: TODO status |  | TODO | bar: October 2026 27
Repo: history rewrite, merge (2 of 2 done)
A6 | History rewrite (untrack_produced.py --run), approved Oct 27 with conditions: git bundle backup and a sha256 list of every file under results/, finetune/data/,… | done | Ritik | 2026-10-26 | 2026-10-27 | start: TODO From; end: TODO From (no done date) (inferred) | decision: plan for main | TODO | bar: October 2026 26 to October 2026 27
A7 | Merge trackA-nosol into local main (shared code, docs, no produced data); tests; push commands for Ritik | done | Ritik | 2026-10-27 | 2026-10-30 | start: TODO From; end: TODO status |  | TODO | bar: October 2026 27 to October 2026 30
Evaluation and Gate 3 (3 of 7 done)
A14 | Gate 3 job plan: every job in order, 2 at a time, limits, dates | done | Ritik | 2026-10-26 | 2026-10-27 | start: TODO From; end: TODO status |  | TODO | bar: October 2026 26 to October 2026 27
A16 | Evaluate base, prompt-only and the trained versions on Sol (batch 3) | in progress | Ritik | 2026-10-26 | 2026-11-09 | start: TODO From; end: before A18 (it waits on it) (inferred) |  | TODO | bar: October 2026 26 to November 2026 9
A17 | Step 13 analysis: 4 measures, hiding check, false-disclosure check, measure 4 on hand-label categories, "tags help more on the inserted tool turn than the past… | planned | Ritik | 2026-11-10 | 2026-11-20 | start: PLAN timeline; end: PLAN timeline (Nov 10–Nov 20): Step 13 analysis | A16, L4 | TODO | bar: November 2026 10 to November 2026 20
A18 | Look-inside rerun on the best version (L1): Step 10 drops at 15/19/23; heads L19H31, L23H17, L15H31: drop, or stay while the answer stops following | planned | Ritik | 2026-11-04 | 2026-11-09 | start: PLAN timeline; end: PLAN timeline (Nov 4–Nov 9): look inside the best version (L1) | A16 | TODO | bar: November 2026 4 to November 2026 9
A21 | Hand the best version to Tracks B and C (week 15) | planned | Ritik | 2026-11-23 | 2026-11-29 | start: PLAN timeline; end: PLAN timeline (Nov 23–Nov 29): Hand the best version to B and C | A16 | TODO | bar: November 2026 23 to November 2026 29
A33 | Hugging Face generation for batch 3 (Ritik, Oct 29: all systems and B1 on the training environment's stack; vLLM optional): finetune/hf_engine.py (continuous b… | done | Ritik | 2026-10-29 | 2026-10-29 | start: TODO From; end: TODO status |  | TODO | bar: October 2026 29
A36 | Gate 3 in one command (Ritik, Oct 29): finetune/gate3.py --out results/trackA/gpu/eval runs eval.py's report, then writes the verdict per trained version (the… | done | Ritik | 2026-10-29 | 2026-10-30 | start: TODO From; end: TODO status |  | TODO | bar: October 2026 29 to October 2026 30
S7: validation loss (1 of 1 done)
A28 | Training needs a baseline (Ritik, Oct 28): the validation loss of base and both epochs of every version (lora, tags, lora_tags, lora_attn3; all four decided Oc… | done | Ritik | 2026-10-28 | 2026-10-28 | start: TODO From; end: TODO status | A15 | TODO | bar: October 2026 28
Set A (2 of 2 done)
A29 | Set A, an independent localization set (Ritik, Oct 29): Olmo 3 7B Think on the 34 validation questions (pasted and declared inserted tool turn, 3 runs each; St… | done | Ritik | 2026-10-29 | 2026-10-30 | start: TODO From; end: TODO status |  | TODO | bar: October 2026 29 to October 2026 30
A32 | Rank heads on set A (Step 9 rerun) for B1's head-subset variant; never on the evaluation questions | done | Ritik | 2026-10-29 | 2026-10-30 | start: TODO From; end: TODO status | A29 | TODO | bar: October 2026 29 to October 2026 30
B1: provenance scaling (0 of 1 done)
A30 | B1, provenance-scaled attention at inference (finetune/provenance.py): the forced-answer job on set A's cuts (chooses alpha on set A), then generation on the 3… | in progress | Ritik | 2026-10-29 | 2026-11-20 | start: TODO From; end: PLAN: all evaluation done by (inferred) | A29 | TODO | bar: October 2026 29 to November 2026 20
B2: provenance bias (0 of 1 done)
A31 | B2, provenance-gated attention bias (versions gate3, lora_attn3_gate in train.py): a learned per-head bias on tool-tagged keys in 15/19/23, zero-initialized; L… | planned | Ritik | 2026-10-29 | 2026-11-20 | start: TODO From; end: PLAN: all evaluation done by (inferred) | batch 3's order | TODO | bar: October 2026 30 to November 2026 20
Thread 1 on Qwen3-8B (0 of 1 done)
A37 | Thread 1 on a second model (Ritik, Oct 30): Qwen3-8B thinking on, Step 3 and Step 10 on Track B's runs; localize on the 24 pilot puzzles (tool_real), replicate… | blocked | Ritik | 2026-10-30 | 2026-11-20 | start: TODO From; end: PLAN: all evaluation done by (inferred) | the push; the 10 jobs | TODO | bar: October 2026 30 to November 2026 20
Track B: test widely
Closed models, GPQA (0 of 4 done)
B1 | Closed-provider keys: a real OpenAI key (the current one is the Voyager key), Anthropic, xAI | blocked | Arsha (from Nov 3) | 2026-10-05 | not in the repo | start: TODO From; end: not in the repo | keys | TODO | bar: October 2026 5 to October 2026 30
B2 | Is Claude Haiku 4.5 still served? Swap in its replacement if not (Haiku 5.5 needs an adapter change) | planned | Arsha (from Nov 3) | not in the repo | not in the repo | start: not in the repo; end: not in the repo | B1 | TODO
B3 | Closed-model smoke tests (run_trackB.py --run --only-provider X --limit 1) | blocked | Arsha (from Nov 3) | 2026-10-25 | not in the repo | start: TODO From (inferred); end: not in the repo | B1, "go" (paid) | TODO | bar: October 2026 25 to October 2026 30
B6 | GPQA Diamond: export to data/gpqa_diamond.jsonl (gitignored); nothing from it in any doc or tracked file | blocked | Arsha (from Nov 3) | not in the repo | not in the repo | start: not in the repo; end: not in the repo | Ritik accepts its terms on Hugging Face and says so | TODO | bar: October 2026 30
Voyager models (B5, B7–B15) (9 of 10 done)
B5 | Olmo 3 7B Think in Track B through the pinned Think format on /v1/completions (olmo_format.py), with the declared tool_injected channel in place of tool_real | done | Ritik | 2026-10-21 | 2026-10-27 | start: TODO From; end: commit fb9b5c1 (inferred) |  | TODO | bar: October 2026 21 to October 2026 27
B7 | Voyager runs, 3 per question, the 24 puzzles and the 30 MMLU-Pro items, all conditions: Qwen3 30B Thinking, then Qwen3 30B Instruct, then Olmo 3 7B Think | done | Ritik | 2026-10-27 | 2026-10-28 | start: TODO From; end: TODO status |  | TODO | bar: October 2026 27 to October 2026 28
B8 | steered_cases.jsonl: define the format (no code writes it today), then export from B7 | done | Ritik | 2026-10-27 | 2026-10-28 | start: TODO From; end: TODO status | B7 | TODO | bar: October 2026 27 to October 2026 28
B9 | The Gate 2 question: is the tool-vs-user gap still clear with 3 runs per question and more models? Answered as soon as the data allows | in progress | Arsha (from Nov 3) | 2026-10-27 | 2026-11-08 | start: TODO From; end: Gate 2 (PLAN) | B14 | TODO | bar: October 2026 27 to November 2026 8
B10 | Served chat template per Voyager model (prompt-token count against a local rendering, as for Olmo on Oct 21), recorded | done | Ritik | 2026-10-27 | 2026-10-27 | start: TODO From; end: TODO From (no done date) (inferred) |  | TODO | bar: October 2026 27
B11 | Identity-canary references for every Voyager model Tracks B and C use, before their first batch | done | Ritik | 2026-10-27 | 2026-10-27 | start: TODO From; end: TODO From (no done date) (inferred) |  | TODO | bar: October 2026 27
B12 | A model flag for run_trackB.py | done | Ritik | 2026-10-27 | 2026-10-27 | start: TODO From; end: commit fb9b5c1 (inferred) |  | TODO | bar: October 2026 27
B13 | Per model: smoke test (--limit 5) and the dry run (calls, hours) in a session log; then the run starts | done | Ritik | 2026-10-27 | 2026-10-27 | start: TODO From; end: the session log it names |  | TODO | bar: October 2026 27
B14 | Track B table: model × channel × thinking (on/off where it exists); hint following against the per-letter no-hint baseline; sure and unsure questions; mention… | done | Ritik | 2026-10-27 | 2026-10-28 | start: TODO From; end: TODO status | B7, B4 | TODO | bar: October 2026 27 to October 2026 28
B15 | Can a prompt bring the tool back into the final answer? (Ritik, Oct 29) Qwen3 30B Thinking and Instruct, Track B's 54 questions, 3 runs, with "In your final an… | done | Ritik | 2026-10-29 | 2026-10-30 | start: TODO From; end: TODO status |  | TODO | bar: October 2026 29 to October 2026 30
Qwen3-8B, thinking on and off (1 of 1 done)
B4 | Qwen3-8B, thinking on and off, real tool calls: on Sol (our vLLM server, enable_thinking), core cells first; replaces the Ollama grid (decided Oct 28: Ollama n… | done | Ritik | 2026-10-27 | 2026-10-30 | start: TODO From; end: TODO status |  | TODO | bar: October 2026 27 to October 2026 30
Track C: multi-agent pipeline
Team code (4 of 4 done)
C2 | No-tool team (the solver always gets the tool today) | done | Ritik | 2026-10-27 | 2026-10-27 | start: set to the done date (inferred); end: commit b72b747 (inferred) |  | TODO | bar: October 2026 27
C3 | Second reviewer model (hard-coded today) | done | Ritik | 2026-10-27 | 2026-10-28 | start: TODO From; end: TODO status |  | TODO | bar: October 2026 27 to October 2026 28
C6 | run_team.py: append-only, writing to gitignored results/trackC/ (today it deletes its own log and writes to tracked results/scope/) | done | Ritik | 2026-10-22 | 2026-10-27 | start: TODO From; end: commit b72b747 (inferred) |  | TODO | bar: October 2026 22 to October 2026 27
C7 | Input-file option for run_team.py (live takes pilot puzzles only) | done | Ritik | 2026-10-27 | 2026-10-27 | start: TODO From; end: commit b72b747 (inferred) |  | TODO | bar: October 2026 27
Experiments (13 of 19 done)
C1 | Live team on 5 items (run_team.py --live --n 5) | done | Ritik | 2026-10-25 | 2026-10-27 | start: TODO From (inferred); end: TODO status |  | TODO | bar: October 2026 25 to October 2026 27
C4 | The team on Track B's steered cases (Qwen3 Thinking's first), 3 repeats, tool and no-tool teams, both reviewers (--log team_c4) | done | Ritik | 2026-10-27 | 2026-10-28 | start: TODO From; end: TODO status | B8, C2, C3, C7 | TODO | bar: October 2026 27 to October 2026 28
C5 | Track C table per reviewer variant: shipped, caught, false alarms, undetermined; bad and good lookups apart; the checker's disagreement against the no-tool tea… | done | Ritik | 2026-10-27 | 2026-10-28 | start: TODO From; end: TODO status | C4 | TODO | bar: October 2026 27 to October 2026 28
C9 | Does an instruction restore the reviewer's check? (Ritik, Oct 28) Only the reviewers again, on C4's saved tool-team cases (no solver or checker calls), with "T… | done | Ritik | 2026-10-28 | 2026-10-28 | start: TODO From; end: TODO status | C4 | TODO | bar: October 2026 28
C10 | Commit first (Ritik, Oct 28): only the reviewers' second step again on C4's saved cases: C9's answer_only review first (its reply as the assistant turn), then… | done | Ritik | 2026-10-28 | 2026-10-28 | start: TODO From; end: TODO status | C9 | TODO | bar: October 2026 28
C11 | Is the deference general? Two more reviewer models on C4's saved cases with C4's prompt (Olmo 3 7B Instruct, Qwen3 30B Thinking); pre-registered rule in the Oc… | done | Ritik | 2026-10-29 | 2026-10-29 | start: TODO From; end: TODO status | C4 | TODO | bar: October 2026 29
C12 | What is the cue? Both C4 reviewers with every statement of the tool's letter redacted (private reasoning; tool log); against C4's unredacted variants and answe… | done | Ritik | 2026-10-29 | 2026-10-29 | start: TODO From; end: TODO status | C4 | TODO | bar: October 2026 29
C13 | A third and fourth family (Ritik, Oct 29): IBM Granite 4.1 30B and Mistral Small 3.2 24B Instruct (Apache 2.0, not gated; non-thinking, like C4's pair) as revi… | done | Ritik | 2026-10-29 | 2026-10-30 | start: TODO From; end: TODO status | set A's three jobs; the snapshots (get_c13) | TODO | bar: October 2026 29 to October 2026 30
C14 | Disagreement as a signal (Ritik, Oct 29; exploratory, no calls): escalate when a reviewer's answer_only review and its trace-seeing review give different lette… | done | Ritik | 2026-10-29 | 2026-10-29 | start: TODO From; end: TODO status |  | TODO | bar: October 2026 29
C15 | Fresh-case replication (Ritik, Oct 29): 100 new items (60 MMLU-Pro outside the evaluation categories, 40 puzzles; none in Track B's 54, the 30 evaluation quest… | done | Ritik | 2026-10-29 | 2026-10-30 | start: TODO From; end: TODO status |  | TODO | bar: October 2026 29 to October 2026 30
C16 | Does a final answer that names the tool change the reviewer's check? (Ritik, Oct 30) C15's 100 fresh items, tool team, the solver told B15's instruction (run_t… | done | Ritik | 2026-10-30 | 2026-10-30 | start: TODO From; end: the session log it names |  | TODO | bar: October 2026 30
C17 | Does naming the source cause the deferring reviewer's drop? (Ritik, Oct 30) C15's saved final answers + a fixed sentence naming the lookup tool vs one naming o… | done | Ritik | 2026-10-30 | 2026-10-30 | start: TODO From; end: the session log it names |  | TODO | bar: October 2026 30
C18 | H33: is the cue the argument? (Ritik, Oct 30) C16's 34 named bad-lookup answers, unchanged vs the tool-citing sentences removed (run_team.py --final-edit strip… | done | Ritik | 2026-10-30 | 2026-10-30 | start: TODO From; end: the session log it names |  | TODO | bar: October 2026 30
C19 | H34: is an authority claim the cue? C15's bare answers + an answer-key citation sentence vs an own-working sentence of the same length; Olmo 3.1 32B and Qwen3… | planned | Shrey (from Oct 30) | 2026-10-30 | 2026-11-05 | start: TODO From; end: TODO row |  | TODO | bar: October 2026 30 to November 2026 5
C20 | A structural fix: the trace withheld, or a blind first review that only reports disagreement; pipelines on C15's items against the checker (TRACK_C §8, 2) | planned | Shrey (from Oct 30) | 2026-10-30 | 2026-11-09 | start: TODO From; end: TODO row |  | TODO | bar: October 2026 30 to November 2026 9
C21 | Items the solver can't answer without the tool, where the checker's floor rises (fresh MMLU-Pro outside the 30) (TRACK_C §8, 3) | planned | Shrey (from Oct 30) | 2026-10-30 | 2026-11-13 | start: TODO From; end: TODO row |  | TODO | bar: October 2026 30 to November 2026 13
C22 | Another solver model (Olmo 3 7B Think or Qwen3 30B Instruct's steered cases), C4's design (TRACK_C §8, 4) | planned | Shrey (from Oct 30) | 2026-10-30 | 2026-11-17 | start: TODO From; end: TODO row |  | TODO | bar: October 2026 30 to November 2026 17
C23 | A pre-registered set of reviewer wordings on C4's cases, Olmo 3.1 32B (TRACK_C §8, 5) | planned | Shrey (from Oct 30) | 2026-10-30 | 2026-11-19 | start: TODO From; end: TODO row |  | TODO | bar: October 2026 30 to November 2026 19
C24 | Thread 2's paper figures and tables (TRACK_C §8, 6) | planned | Shrey (from Oct 30) | 2026-10-30 | 2026-11-22 | start: TODO From; end: TODO row |  | TODO | bar: October 2026 30 to November 2026 22
Labels
Labels L1–L5 (2 of 5 done)
L1 | Replace the 10 label-queue rows with no text: no calls, the original rule (random hinted pilot runs with saved text, seed recorded), marked as replacements in… | done | Ritik | 2026-10-27 | 2026-10-27 | start: TODO From; end: commit d41f77e (inferred) |  | TODO | bar: October 2026 27
L2 | Labeling kit: two blank rater sheets from LABEL_QUEUE.csv (keyword columns hidden), the guide, a kappa-per-channel script that lists disagreements (no labels f… | done | Ritik | 2026-10-27 | 2026-10-27 | start: TODO From; end: commit d41f77e (inferred) |  | TODO | bar: October 2026 27
L3 | Label the queue, two raters; Cohen's kappa per channel; under 0.6, tighten the guide and label a fresh batch | blocked | Ritik | not in the repo | 2026-11-08 | start: not in the repo; end: Gate 2 (PLAN) | raters | TODO | bar: October 2026 30 to November 2026 8
L4 | Gate 3's labeling sheets (Ritik, Oct 30: blind, no system or candidate marks; no part only candidates): part 1 = LoRA's 147 false-disclosure candidates + 147 m… | blocked | Ritik | 2026-10-25 | 2026-11-20 | start: TODO From; end: before A17 (it waits on it) (inferred) | A16; the push | TODO | bar: October 2026 25 to November 2026 20
L5 | Track B labeling batch (tools/label_kit.py trackb), labeled in order: group 1, Qwen3 Thinking's runs that followed after a real call or with the pasted block (… | blocked | Ritik | 2026-10-28 | not in the repo | start: TODO From; end: not in the repo | L3 | TODO | bar: October 2026 28 to October 2026 30
Repo, docs and handoff
Handoffs, repo, docs (4 of 6 done)
H1 | Start trackB-main and trackC-main from main | done | Ritik | 2026-10-27 | 2026-10-28 | start: TODO From; end: TODO status | A7, the push | TODO | bar: October 2026 27 to October 2026 28
H2 | docs/handoff/TRACK_B.md, for Arsha: what's done, results (FINDINGS links), how to run each step (RUNBOOK), open items, inherited decisions, traps; current all… | in progress | Ritik | 2026-10-27 | 2026-11-03 | start: TODO From; end: TODO row |  | TODO | bar: October 2026 27 to November 2026 3
H3 | docs/handoff/TRACK_C.md, for Shrey: the same | done | Ritik | 2026-10-27 | 2026-10-30 | start: TODO From; end: TODO status |  | TODO | bar: October 2026 27 to October 2026 30
H4 | tools/make_handoff_bundle.py: a tar.gz per track of its gitignored results, with a sha256 manifest; GPQA files never inside unless Ritik says so | done | Ritik | 2026-10-27 | 2026-10-27 | start: TODO From; end: commit 87f3357 (inferred) |  | TODO | bar: October 2026 27
R1 | GitHub main still has the old Voyager IDs: runs from GitHub fail the Oct 21 routing | done | Ritik | 2026-10-21 | 2026-10-30 | start: TODO From; end: TODO status |  | TODO | bar: October 2026 21 to October 2026 30
R2 | The pre-push hook is installed only on this Mac; each teammate installs it (RUNBOOK, repo hygiene) | planned | Ritik | 2026-10-26 | not in the repo | start: TODO From; end: not in the repo |  | TODO
Standing duties (0 of 4 done)
D1 | Docs kept in line with the code and results; each says when it was last updated | in progress (standing) | Ritik | 2026-10-27 | not in the repo | start: TODO From; end: not in the repo |  | TODO | bar: October 2026 27 to October 2026 30
D2 | Session logs after every run and every stop: docs/sessions/YYYY-MM-DD_HHMM_<A¦B¦C¦ALL>_<name>.md, LATEST.md, INDEX.md | in progress (standing) | Ritik | 2026-10-27 | not in the repo | start: TODO From; end: not in the repo |  | TODO | bar: October 2026 27 to October 2026 30
D3 | A daily log at the end of each day, docs/sessions/DAILY_YYYY-MM-DD.md | in progress (standing) | Ritik | 2026-10-27 | not in the repo | start: TODO From; end: not in the repo |  | TODO | bar: October 2026 27 to October 2026 30
H5 | Teammates' work on GitHub: check before every merge; never overwrite; report it in a log; merge only on Ritik's say | in progress (standing) | Ritik | 2026-10-27 | not in the repo | start: TODO From; end: not in the repo |  | TODO | bar: October 2026 27 to October 2026 30
Milestones: gates, handoffs, presentations, report
Gates (1 of 3 done)
Gate 1 | Gate 1: missed (recorded Oct 27); the fallback applies: Voyager and Ollama for B, Voyager for C (… | done | everyone | 2026-10-25 | 2026-10-25 | start: PLAN; end: PLAN |  | PLAN | bar: October 2026 25
Gate 2 | Gate 2: the tool-vs-user gap (B9) and the hand labels with kappa (L3) | planned | everyone | 2026-11-08 | 2026-11-08 | start: PLAN; end: PLAN | B9, L3 | PLAN | bar: November 2026 8
Gate 3 | Gate 3: a trained version follows fewer wrong hints, accuracy within 5 points, hiding check not up | planned | everyone | 2026-11-22 | 2026-11-22 | start: PLAN; end: PLAN | A17 | PLAN | bar: November 2026 22
Handoffs (1 of 2 done)
Handoff B | Track B to Arsha | planned | Arsha | 2026-11-03 | 2026-11-03 | start: the owner rule; end: the owner rule |  | owner rule | bar: November 2026 3
Handoff C | Track C to Shrey | done | Shrey | 2026-10-30 | 2026-10-30 | start: the owner rule; end: the owner rule |  | owner rule | bar: October 2026 30
Presentations and report (1 of 4 done)
Progress talk | Progress presentation (v3 presented; date not in the repo) | done | everyone | not in the repo | not in the repo | start: not in the repo; end: not in the repo |  | OVERVIEW
Draft report | Draft report (exact day not in the repo) | planned | Ritik | 2026-11-23 | 2026-11-29 | start: PLAN timeline window; end: PLAN timeline window (its end) (inferred) |  | PLAN | bar: November 2026 23 to November 2026 29
Final presentation | Final presentation (week 16) (exact day not in the repo) | planned | everyone | 2026-11-30 | 2026-12-06 | start: PLAN timeline window; end: PLAN timeline window (its end) (inferred) |  | PLAN | bar: November 2026 30 to December 2026 6
Final report | Final report (exact day not in the repo) | planned | Ritik | 2026-12-07 | 2026-12-12 | start: PLAN timeline window; end: PLAN timeline window (its end) (inferred) |  | PLAN | bar: December 2026 7 to December 2026 12

## Daily
Date | Day | Track | What was done | Runs and compute (as logged) | Findings added | Commits | Hashes | Sources
2026-10-02 | Fri | Setup and the progress round | From commits (no session log before Oct 27): Add hint-acknowledgment harness, results, and progress deck ¦ Final progress-round results and plain-language slides |  |  | 2 | 69ffa33 e50f343 | git log (inferred)
2026-10-04 | Sun | Setup and the progress round | From commits (no session log before Oct 27): Rework progress slides for first-time viewers ¦ Progress run phase 0-1: shared helpers, timing run, model manifest ¦ Experiment A: reviewer demo on real cue-steered answers (demo, n=5+6) ¦ Truncation sweep (3c): leak follows request mode, not the cap ¦ Experiment B: no-cue screen on 30 MMLU-Pro items (180 calls, 0 errors) ¦ Experiment B results, figures F1-F9, evidence viewer, screenshots, docs ¦ Address review: answered-only cue rates, guard tie rule, hint-in-text caveat ¦ added current ppt ¦ updated gitignore ¦ Add progress-round experiments, figures and notes ¦ Restore .gitignore rules and .env.example ¦ Add tool-hint, reviewer and leak results to the progress deck ¦ Scope update part 1: private/final mention overlap and Test 2 combined counts ¦ Scope update part 3: provider adapters, budget guard, real tool calls, Track B/C/A scaffolds ¦ Scope update part 2: docs for the new scope, plan, tracks and budget ¦ Demo UI for the progress presentation ¦ Merge branch 'demo-ui' into main ¦ Add v3 of the progress presentation deck ¦ Interactive wrong-hint playground ¦ Ui Demo updates |  |  | 20 | 52e246f 3672241 712b0df 1a140b7 a737ef0 960ca6f 566d633 13bf5ca 227be96 76c3c2b 3517b2b 8941bb9 5ac498b b526d3a 338f4b6 5b23d86 fb418c0 2f9cb0a f05b4f4 cdef34a | git log (inferred)
2026-10-05 | Mon | Setup and the progress round | From commits (no session log before Oct 27): Small-question examples and a simpler, visual playground ¦ Playground back to the sidebar + center layout, presentation-ready ¦ Updated UIv2 ¦ Engineering example (Case 6) renamed and moved up; tool-result wording; reasoning opens at the firs… ¦ Updated ppt ¦ Demo v2: the presentation's examples with exactly its runs ¦ Demo v2: one column per hint, presentation numbers, charts page ¦ Final demo: the presentation's runs at /, first playground removed |  |  | 8 | 58d149e 2034153 1edfd70 c0581b8 8d14f58 70f9994 d556782 adc0518 | git log (inferred)
2026-10-06 | Tue | Setup and the progress round | From commits (no session log before Oct 27): updated ppt |  |  | 1 | 0ad378a | git log (inferred)
2026-10-20 | Tue | Track A: explain and fix | From commits (no session log before Oct 27): Docs: one overview, one plan; 15 docs merged and removed |  |  | 1 | 955ebbe | git log (inferred)
2026-10-20 | Tue | Track B: test widely | From commits (no session log before Oct 27): Docs: one overview, one plan; 15 docs merged and removed |  |  | 1 | 955ebbe | git log (inferred)
2026-10-20 | Tue | Track C: multi-agent pipeline | From commits (no session log before Oct 27): Docs: one overview, one plan; 15 docs merged and removed |  |  | 1 | 955ebbe | git log (inferred)
2026-10-21 | Wed | Track A: explain and fix | From commits (no session log before Oct 27): Track A step 1: Voyager capability probe; client: extra fields, /v1/completions, logprobs, error de… ¦ Track A step 1 results: Voyager capability probe on olmo3-7b-think (8 calls + 1 repeated 400) ¦ Track A step 2: pinned Olmo Think format, tool_injected, render-based source tags ¦ Track A step 2b: base-model runner in the pinned format (dry run only); template revision scan (no… ¦ Track A step 2b: declared-functions arm, contradiction count, smoke test ¦ Track A step 2b smoke test: 3 calls, all checks passed ¦ Voyager ID change (Oct 21): routing, prompt-length and identity checks (7 calls); 11 Step 2b runs s… ¦ Track A step 2b: resume through the new Voyager route (guards on, old-route runs rerun and supersed… ¦ Track A step 2b: continue cut-off replies up to the 65,536-token context (automatic for new runs; -… ¦ Client: a list of prompts in one /v1/completions request keeps each prompt's own text, log-probs an… ¦ Track A step 3: takeover curve (probe after every sentence, one request per probe, last probe first… ¦ Track A step 2b report: cut-offs at 16,000 tokens, continued to the context, and still cut off |  |  | 12 | 50bacba c1f312e b225b50 96f536a e3bbb72 06b45ed a0c6066 244bcb1 4eba10e fbd8db5 1b5f871 515e8d6 | git log (inferred)
2026-10-21 | Wed | Track B: test widely | From commits (no session log before Oct 27): Voyager model IDs changed (Oct 21): one mapping, guards in the shared client |  |  | 1 | 019959c | git log (inferred)
2026-10-21 | Wed | Track C: multi-agent pipeline | From commits (no session log before Oct 27): Voyager model IDs changed (Oct 21): one mapping, guards in the shared client |  |  | 1 | 019959c | git log (inferred)
2026-10-21 | Wed | All tracks | From commits (no session log before Oct 27): Updated ppt |  |  | 1 | 15e0047 | git log (inferred)
2026-10-22 | Thu | Track A: explain and fix | From commits (no session log before Oct 27): Track A step 3 pilot: Voyager refuses a list of prompts (HTTP 400), so one probe per request; 78 pr… ¦ Track A step 2b: main run done through the new route (239 of 240 ok; 1 ConnectionResetError being r… ¦ Track A step 2b: 92 cut-off runs continued (90 finished); fix two run faults: a call quoted inside… ¦ Track A step 3: a probe without log-probs fails its run; a curve with a gap is not done and is prob… ¦ Step 2b report: differences as a bootstrap clustered by question (common.boot_diff), declared minus… ¦ Track A step 2b done: 240 of 240 runs ok through the new route; 93 continued past 16,000 tokens (91… |  |  | 6 | 06608eb a6d7bd0 e4ff278 57a79a1 a4da5ac 3856f48 | git log (inferred)
2026-10-24 | Sat | Track A: explain and fix | From commits (no session log before Oct 27): Step 3 report and figures: resisted runs show whether the hint leads before any reasoning and where… ¦ Track A step 3 done: 219 runs, 137,143 probes (early answering, Lanham et al. 2023); report adds co… ¦ Step 3 storage: per-probe records move to takeover_probes.jsonl.gz (15.7 MB, same 228 records, chec… ¦ Before Step 4: concentration of followed runs on sure questions; late takeovers vs resisted runs' c… ¦ Track A step 4: deletion test script (hint mentions vs length-matched control before the takeover c… ¦ Track A storage: files with full replies are gzip by default (base_format 33.8 -> 7.2 MB with a one… ¦ Step 4: unedited arm (3 continuations from the original cut); token cap per case = the original's r… ¦ Before Step 4, 2(a) matched: onsets of the hint's lead after the first fifth, permanent (takeover)… ¦ Track A step 4 done: 19 cases, 209 calls. Forced answer at the cut back to the own answer: hint 7 o… ¦ Parser: read 'Answer' wrapped in markdown bold ('Answer: D', 'the answer is E'); found in a Step 4… ¦ Re-score every saved result with the fixed parser (no calls): 1 letter changes, a Step 4 hint-arm c… ¦ Step 4 report: re-mentions in continuations that end on the hint letter (hint arm 34 of 44, control… ¦ Track A: one continuation for every rerun (finetune/continuation.py). A tool call in the final answ… ¦ Track A step 5: dataset rules (all-correct target rule, no fallback; old majority rule behind a fla… ¦ Before Step 6: length audit split by channel and tool rounds (a run's final sequence counted once;… ¦ Track A steps 6-7 code: training pool (600 questions, prefix-stable, 0 overlap), no-hint runner (pi… ¦ Test: the written dataset's checks follow Step 5 (training empty until Step 6, correct-hint records… ¦ Track A step 6 pilot: 10 questions x 3 no-hint runs; 5 kept (3 disagree, 1 agree on a wrong answer,… ¦ Track A step 7 pilot: 30 records (5 kept questions x 3 channels x wrong/correct), 76 samples; a gui… |  |  | 19 | 5007dd4 b4ff76d 5f01a2b 3d95fc1 9fda7fc 06e7599 82260cd de6888e b880905 66c55ef f9e5037 c799a33 aa1c13c 8c41730 e3dae86 01add40 39fe64c 3a63cf4 4b31f1c | git log (inferred)
2026-10-24 | Sat | All tracks | From commits (no session log before Oct 27): Canary: no reply is not a verdict. Requests pause, the canary retries every 2 minutes, the run resu… |  |  | 1 | 878d80b | git log (inferred)
2026-10-25 | Sun | Track A: explain and fix | From commits (no session log before Oct 27): Track A: prefill targets (reasoning and final-answer openers from 10 paraphrases, no instruction to… ¦ Track A step 7 prefill pilot: 28 of 30 records get a prefill target (note pilot: 18 of 30), 1.43 sa… ¦ Track A steps 6+7 setup: instruction rule narrowed to the guiding note's own phrases; final-answer… |  |  | 3 | 9e67c0e a32096e 69a681b | git log (inferred)
2026-10-26 | Mon | Track A: explain and fix | From commits (no session log before Oct 27): Track A Sol kit, item 1: setup_env.sh (torch 2.14.1+cu130 and pinned packages into /scratch/ragarw6… ¦ Track A Step 8 on Sol: checkpoint_check.py (local bf16 + fp32 forward over Step 1's, the Oct 21 and… ¦ Track A Step 9 on Sol: attn_to_hint.py (one forward pass per hinted Step 2b run; a registered atten… ¦ Track A Step 10 on Sol: patching.py (Step 4's 21 cases; cuts (i) before the first hint mention, 19… ¦ Track A: Step 8 rule fixed before the result (same checkpoint if (a) no first-2,047 mismatch outsid… ¦ Data stays off GitHub: produced folders gitignored (results/trackA¦B¦C, finetune/data, the canary l… ¦ Track A Steps 8-10 results from Sol. Step 8: the Oct 26 rule fails (a) at 4 positions with gaps 0.1… ¦ Track A Step 9 follow-up results and a matched redo. Full-attention layers: tool - user -8.1e-3 [-1… |  | F1, F2, F3, F4, F5, F6, F7, F8, F9, F10, F11, F12, F13 | 8 | 0bcf60e 1de71bb a6085d0 e2cbe93 7ad8cf6 38ef97f 53b5a35 679df2e | git log (inferred)
2026-10-27 | Tue | Track A: explain and fix | 13:55 Steps 6–7 final: 251 kept of 530; Step 7 targets by channel; 1,196 examples assembled (1,040 train, 156 validation; 'neither' dropped) |  | F14 | 19 | c29f29f c2a95b0 256e1b3 f4400da c7c953d df32ccb 8cf0453 41506a3 3848f77 834c0f3 4ad4e85 ebc8dde de6affa 957590b 18cdcfa cbbd936 79ace0b 8125f48 aacf296 | 2026-10-27_1355_A_steps67-final.md
2026-10-27 | Tue | Track B: test widely | 13:05 Track B smoke tests (3 Voyager models, 15 of 15), served-template check, Qwen3 canaries, Ollama pilot and full grid started; Track A Steps 11–13 code and Sol jobs; plan for main (decision) |  |  | 18 | f106ff9 2095782 0584528 81415f7 fc708d7 dda0d6a ebc8dde 87f3357 1ad0a65 d534d19 e4b2206 91689dd 35f7c19 be8f028 6ca141a 8d8e206 8125f48 aacf296 | 2026-10-27_1305_B_smoke-and-pilots.md
2026-10-27 | Tue | Track C: multi-agent pipeline | 15:05 Track C live on 5 items: checker caught 3 of 3 bad lookups, no false alarm; reviewers alone: Qwen3 Instruct corrected 12 of 12, Olmo 3 7B Instruct 0 (cap); reviewer cap raised to 8,000 |  |  | 7 | 94cfc4d 1ad0a65 d534d19 e4b2206 be8f028 6ca141a a0e5527 | 2026-10-27_1505_C_C1-five-items.md
2026-10-27 | Tue | Labels | From commits (no session log for this track that day): Labels: the kit and the 10 replacement rows (L1, L2). tools/label_kit.py build (no calls): the 10 q… ¦ TODO: statuses after Oct 27 (Steps 6-7 done and assembled; rewrite of trackA-nosol done, main waits… ¦ tools/make_handoff_bundle.py (H4): a tar.gz per track of its gitignored results (A: results/trackA,… ¦ RUNBOOK brought up to date (Oct 27 14:10): Steps 6-7 done; Steps 11-13 commands (rsync of inputs, s… ¦ OVERVIEW and PLAN brought up to date (Oct 27 14:55): status per track after today's runs and code,… ¦ Code README: Oct 27 files (Track B report, template check, canaries, label kit, handoff bundles, St… |  |  | 6 | f8149e4 ebc8dde 87f3357 1ad0a65 19d1b75 35f7c19 | git log
2026-10-27 | Tue | All tracks | 10:10 Catch-up on the whole project: Step 9 matched onsets (F14, T9), the Steps 6–7 checkpoint report, the open-work audit (TODO), docs refreshed, Sol Python path fixed ¦¦ 14:00 History rewrite of trackA-nosol (backup, sha256 list identical, 0 produced paths tracked); local main fast-forwarded; push waits on the plan for main; Track B Qwen3 Thinking, Ollama grid and Track C C1 running ¦¦ 14:00 Paused for an hour: Track B Qwen3 Thinking, the Ollama grid and Track C C1 stopped cleanly (resumable) ¦¦ 23:08 First Sol jobs: submit.sh fixed (silent exit, dependencies checked); S2 failed on --disable-log-requests (vLLM 0.31.0), fixed with a CPU check of the server options; Steps 6–7, the training set, the rewrite and the merge: where they stand; Track B stopped (the Mac was slow); T10 ¦¦ 23:55 The class QoS only (submit.sh refuses unlisted QoS before sbatch); data checks (a) 0 held-out questions or wordings, (e) 0 over 32,768; S1 refit and batch-2 lines (plan_training.py, run on Sol); Qwen3-8B moves to Sol (code, tests, 0.5–1.5 GPU h); Track B Voyager runs resumed one model after another ¦¦ Daily: The day across the three tracks, compute used, state at the end of the day, tomorrow | 0.5–1.5 GPU h; compute (daily): Voyager: the end of Steps 6–7; Track B 157 runs (Qwen3 Thinking 147, its smoke included; Qwen3 Instruct and Olmo 3 7B Think 5 each, smoke); C1 77 agent steps (22 of them in the run stopped at the pause).; Sol: S2 12 GPU-minutes (failed); S1 not back yet.; Local: Ollama 22 runs.; No paid calls. |  | 4 | b59d145 8ce47fd d905f1b 39c171d | 2026-10-27_1010_catch-up.md, 2026-10-27_1400_ALL_rewrite-and-merge.md, 2026-10-27_1400_ALL_paused-for-class.md, 2026-10-27_2308_ALL_sol-fixes-and-status.md, 2026-10-27_2355_ALL_qos-training-qwen8b.md, DAILY_2026-10-27.md
2026-10-28 | Wed | Track A: explain and fix | 00:02 vllm serve --help=all fails on a CPU node (CUDA build): setup_vllm checks version and commands against the committed list; each vLLM GPU job compares its node's help with the list first; batch-2 lines sent (8 h limits) |  | F20 | 9 | 1c66f33 49f1f76 b9e648d bb8399a 84e6acb c140107 3cf2044 84151ab 5cdc2d6 | 2026-10-28_0002_A_vllm-options-on-gpu.md
2026-10-28 | Wed | Track B: test widely | 00:45 Track B interim (Qwen3 30B Thinking, 54 q, ~1 run each): following user 2 of 62, pasted 19 of 62, real call 23 of 62 (23 of 23 when it called the tool), Gate 2 clear so far; report leaves out old Ollama rows; a failed Voyager guard now pauses all Voyager work ¦¦ 03:25 Track B Qwen3 30B Thinking final (810 runs, F15): following user 3 of 162, pasted 59, real call 54 (54 of 54 when called; final answer names the tool 3 of 54), system 57; Gate 2 clear (+35, +31); almost all on MMLU-Pro; steered export 24 steered / 29 matched; C4 started (318 cases) | 810 runs; 318 cases | F15, F16, F17 | 14 | 1c66f33 49f1f76 e0b6870 861b17a b9e648d b404516 8aea482 8fb6243 b104426 9199756 bb8399a 84e6acb c140107 5cdc2d6 | 2026-10-28_0045_B_interim-table-and-halt-guard.md, 2026-10-28_0325_B_qwen3-thinking-final-and-c4-start.md
2026-10-28 | Wed | Track C: multi-agent pipeline | 23:19 C10 (commit first), 23:06–23:16, 636 calls, 0 errors (F21): no protection; Olmo with the private reasoning 19 of 73 (C4 6; +18 [+10, +26]) but −56 from its own first answer, with the tool log 5; Qwen3 with the tool log 33 of 73 (C4 56; −32 [−44, −20]) | 636 calls | F18, F19, F21 | 14 | 49f1f76 e0b6870 421c49d 7ac2dc2 8fb6243 b104426 9199756 bb8399a 84e6acb c140107 3cf2044 84151ab 28e93c4 5cdc2d6 | 2026-10-28_2319_C_c10-commit-first.md
2026-10-28 | Wed | Labels | From commits (no session log for this track that day): Sol batch 2: lora and tags done (both epoch 2; validation loss 0.18537 and 0.21401; 3.41 h and 2.81… ¦ Voyager done: Olmo 3 7B Think (FINDINGS F17: Gate 2 clear, pasted +32 [+22, +42], injected +21 [+13… ¦ vllm_check 66862780 refused at the preflight on --mm-processor-device (a cuda choice on sg018, an o… |  |  | 3 | bb8399a 84e6acb c140107 | git log
2026-10-28 | Wed | All tracks | 00:32 A27: Voyager's Olmo 32B Instruct is 3.1 (template gap 0 in 4 of 5); the 32B reviewer's smoke 5 of 5 (20 of 20 letters; alone: 3 of 3 corrections from the answer or explanation, 0 of 3 with the reasoning or tool log); Sol prep: batch-3 planner, Qwen3-8B download job, budget and template hash ¦¦ 05:45 Track B Qwen3 30B Instruct final (810 runs, F16): following user 1 of 162, pasted 35, real call 147 (calls 162 of 162), system 35; Gate 2 clear (+21, +90); thinking − Instruct: real call −57, pasted +15, system +14; C4 interim 102 of 318 (Olmo 32B reviewer corrects bad lookups 19 of 23 from the answer, 2 of 23 with the private reasoning); Instruct export held until C4 is done; run_team --case-model ¦¦ 12:20 Sol: lora and tags done (epoch 2; validation loss 0.1854, 0.2140); lora_tags and lora_attn3 got no version (submit.sh now refuses train/eval without one); vllm_check's 180 s help limit (now 900 s, with vLLM's traceback); decisions 1–7 (no C4 switch); F15/F16: after a real call the final answer is a bare letter (51 of 54; 111 of 147), real − pasted naming −86 and −62 points; the Track B labeling batch (295 rows, F15's contrast first); branches trackB-main, trackC-main ¦¦ 18:23 Voyager done: Olmo 3 7B Think (F17; Gate 2 clear, +32 / +21; bare answers follow the system turn) and C4 (F18; 0 of 75 wrong shipped, checker 73 of 75; the Olmo 32B reviewer alone corrects 59 of 73 from the answer, 6 with the private reasoning, 3 with the tool log: −73 / −77, paired); the bare letter is about tool use (C4: good lookups 80 of 84, bad 71 of 75, no tool 2 of 159; F15 reworded); S7, the validation loss by taught tokens (6.4%), coded; Track B labeling 151 rows (bare by rule, 10% spot check); Sol resubmissions 66862721/26/80, cause 1 confirmed ¦¦ 21:44 vllm_check 66862780 refused on an unused option (--mm-processor-device): the committed list is sg018's and the preflight refuses only what the server commands use; the Mac's Python crash reports were the preflight test's SIGABRT (now SIGUSR1 + kill); S7 on all four versions (45–80 GPU-min, --estimate 1.25); the keyword check (20 rows of private reasoning, 171 rows); FINDINGS: the story so far, F18 both sides (as good as the tool: 92 and 89 of 159 vs 84), automation bias; C9's dry run (159 cases, 954 calls) and start at 21:46 ¦¦ 22:42 Training against base (S7, 0:37:09, F20): LoRA −58% on the taught tokens (−40% without the opener; the rest −19%), tags −17%, lora_tags ≈ lora, lora_attn3 −52%; val_loss.py --report (clustered by question); C9 done (F19): the sentence doesn't restore the Olmo reviewer's check (6 → 8, 3 → 4 of 73); Sol queue 10 of 10 (vllm_check 66878660, Qwen3-8B 66879362, 8 eval parts) ¦¦ 23:03 F20's tags check from S7's files: lora_tags − lora on the taught tokens +0.0009 [+0.0004, +0.0014] (+0.5%), injected − pasted +0.0003 [−0.0008, +0.0015]: the prediction (tags help most on the inserted turn) isn't borne out in the loss; F20 now leads with lora_attn3 (1.6 M parameters, 85–90% of LoRA's drop,… | 810 runs; Sol jobs 66862721; 159 cases; 954 calls; 45–80 GPU-min; Sol jobs 66862780; Sol jobs 66878660, 66879362; 636 calls; compute (daily): Voyager: Track B: 1,559 runs, about 1,769 calls (Thinking 663 runs, Instruct 805, Olmo 91 by 07:00), with 0 errors. C4: 1,104 agent steps by 07:00 (856 reviews, 124 solver, 124 checker). The 32B smoke: 30 agent steps, plus its canary and template check.; Sol (Ritik's jobs): setup_vllm (CPU); batch 2 training, 4 GPU jobs (about 13.3 GPU-hours at the refit's middle).; Mac: no local model, no Ollama, the power guard on (AC 100% all night).; No paid calls.; Voyager: Olmo 3 7B Think: 716 runs, 8.35 million output tokens. C4: 198 cases, 1,762 agent steps. 0 errors; the guards ended at 17:52 and 17:53.; Sol: lora 3.41 GPU h and tags 2.81 GPU h, mostly overnight; the three failed jobs, about 3 minutes in all; 630 GPU-minutes now pending.; Paid calls: none. |  | 0 |  | 2026-10-28_0032_ALL_32b-reviewer-and-sol-prep.md, 2026-10-28_0545_ALL_qwen3-instruct-final-and-c4-interim.md, 2026-10-28_1220_ALL_sol-fixes-decisions-and-the-bare-letter.md, 2026-10-28_1823_ALL_c4-olmo-done-and-the-bare-letter-control.md, 2026-10-28_2144_ALL_vllm-rule-keyword-check-and-c9-dry-run.md, 2026-10-28_2242_ALL_training-against-base-and-c9.md, 2026-10-28_2303_ALL_tags-check-and-c10-dry-run.md, DAILY_2026-10-28.md
2026-10-29 | Thu | Track A: explain and fix | From commits (no session log for this track that day): Attribution made accurate: every session log's By line, every next-step line and every past-work ow… ¦ Night of Oct 29, before the runs: set A (finetune/setA.py: the 34 validation questions, in neither… ¦ B1 and B2 coded (no runs): provenance-scaled attention at inference (finetune/provenance.py: log(al… ¦ Batch 3 and Qwen3-8B on Hugging Face generation (vLLM failed to start on Sol twice, Oct 29: S2 6687… ¦ vLLM on Sol fixed (Oct 29): the server starts with VLLM_USE_FLASHINFER_SAMPLER=0, because vLLM 0.31… ¦ Qwen3-8B 66934413's ImportError was a thread race, not the environment (Oct 29): Track B's runner r… ¦ Two parts of one system on vLLM, safe together (Oct 29). One server log per part, named like its re… ¦ C13 coded (no runs): a third and fourth reviewer family on Sol, IBM Granite 4.1 30B (ibm-granite/gr… ¦ Session log 16:45: Ritik's nine items. ef6afd8 and the vLLM fix pushed; Qwen3-8B 66934413 was a Pyt… ¦ Sol's clone onto GitHub's history, and the import check's vLLM limit (Oct 29, 21:16). Sol's clone c… ¦ C14 done, C15 and B15 pre-registered before they run (Oct 29, 23:00). C14 (exploratory, no calls; a… ¦ Gate 3 in one command, the rater guide, the handoffs and the paper pack with C11-C15 and B15 (Oct 2… |  |  | 12 | 487d47d 6aabe46 0bd2241 c8d0586 7931b79 28d68a4 ad7ce06 26b008a 8f9e495 427f39e 7e0bae4 f688e31 | git log
2026-10-29 | Thu | Track B: test widely | From commits (no session log for this track that day): Attribution made accurate: every session log's By line, every next-step line and every past-work ow… ¦ Batch 3 and Qwen3-8B on Hugging Face generation (vLLM failed to start on Sol twice, Oct 29: S2 6687… ¦ vLLM on Sol fixed (Oct 29): the server starts with VLLM_USE_FLASHINFER_SAMPLER=0, because vLLM 0.31… ¦ Qwen3-8B 66934413's ImportError was a thread race, not the environment (Oct 29): Track B's runner r… ¦ C14 done, C15 and B15 pre-registered before they run (Oct 29, 23:00). C14 (exploratory, no calls; a… ¦ Gate 3 in one command, the rater guide, the handoffs and the paper pack with C11-C15 and B15 (Oct 2… |  |  | 6 | 487d47d c8d0586 7931b79 28d68a4 7e0bae4 f688e31 | git log
2026-10-29 | Thu | Track C: multi-agent pipeline | From commits (no session log for this track that day): Attribution made accurate: every session log's By line, every next-step line and every past-work ow… ¦ Night of Oct 29, before the runs: set A (finetune/setA.py: the 34 validation questions, in neither… ¦ Set A, C11 and C12 done on Voyager (Oct 29, pre-registered in the 00:20 log). Set A: 204 runs, 39 l… ¦ C13 coded (no runs): a third and fourth reviewer family on Sol, IBM Granite 4.1 30B (ibm-granite/gr… ¦ C14 done, C15 and B15 pre-registered before they run (Oct 29, 23:00). C14 (exploratory, no calls; a… ¦ Gate 3 in one command, the rater guide, the handoffs and the paper pack with C11-C15 and B15 (Oct 2… |  | F22, F23 | 6 | 487d47d 6aabe46 ef6afd8 26b008a 7e0bae4 f688e31 | git log
2026-10-29 | Thu | Labels | From commits (no session log for this track that day): Gate 3 in one command, the rater guide, the handoffs and the paper pack with C11-C15 and B15 (Oct 2… |  |  | 1 | f688e31 | git log
2026-10-29 | Thu | All tracks | 00:20 The night's dry runs, each with its main comparison and decision rule before it runs: set A (34 validation questions, 204 runs, Step 3 probes, cases for Steps 9 and 10 on Sol: does the readout at 15/19/23 replicate?), C11 (Olmo 3 7B Instruct and Qwen3 30B Thinking as reviewers, 954 calls), C12 (the tool's letter redacted, 636 calls); started 00:20 under one power guard ¦¦ 08:10 vLLM failed to start on Sol twice (S2 66878660, Qwen3-8B 66879362: warmup_kernels, root-cause line not yet seen); batch 3 and Qwen3-8B on Hugging Face generation (hf_engine.py, sol_hf.py): continuous batching after a GPU self-check, tags as token ids, sampling from the snapshot (top_p 0.95); per-part files; four fixes (static batches hung on errors, the fallback's attention, step8/9/10/smoke dropped arguments, unbalanced parts); plan_eval.py for Hugging Face: 70–120 tokens/s (estimate), 27–60 GPU h per system, 10 parts of ~6 h; Qwen3-8B 10–15 GPU h; set A resumed 07:58 ¦¦ 10:55 Set A done on Voyager (204 runs; 39 late takeovers on 16 sure questions; Sol jobs sized: Step 10 66 cuts ~80 min, Step 9 ~12 min, B1 forced ~18 min); C11 (F22): Olmo 3 7B Instruct defers (−42 [−58, −28]), Qwen3 30B Thinking doesn't (+1): the family fits, not size or thinking; C12 (F23): redacting the tool's letter restores part of Olmo 32B's check (6 → 23, 3 → 24 of 73; answer only 59), all on matched puzzles ¦¦ 16:45 Ritik's nine items: ef6afd8 + the vLLM fix pushed; Qwen3-8B 66934413 was a Python 3.11 thread race on transformers' first import (47 of 48 threads, reproduced; a lock; envs/olmo fine, no leak), import check in every Sol job; vllm_check 66920320 failed at the tagged server's start (the HF reference's 14.5 GiB), 66928369 passed: LoRA and tags on vLLM; per-part server logs and per-job model directories (release lora after the pull); C13 pre-registered (Granite 4.1 30B, Mistral Small 3.2 24B; 954 reviews, 0.6–1.5 A100 h); F23's split restated as H23; Sol commands in order ¦¦ 23:00 Ritik's decisions (the order of the 10 unsubmitted Sol jobs, with lines; LR_GATE 1e-2 approved, every bias logged, the bound is the applied 1.31 not 2.6; H23 on fresh cases); C14 (exploratory, no calls): two disagreeing reviews never beat the checker's pipeline on catches (56–73 of 73 vs 73), Olmo +12 to +21 false alarms, Qwen3 about equal at ~⅓ of the tokens; C15 pre-registered (100 fresh items; F18 by C11's rule, H23, C14's frozen rule) and B15 (one instruction to name the tool; naming after a call, the bare letter, following); both started 22:48 under the power guard ¦¦ 23:30 Gate 3 in one command (finetune/gate3.py: verdicts, table, two figures; the Oct 25 rule; tested on synthetic files of the real shape); B1's alpha rule fixed since 0bd2241; B2's bias log and drift check; the one-page rater guide (L3, L5); TRACK_B and TRACK_C handoffs, CLAIMS and REVIEWER_QUESTIONS updated with C11–C15 and B15; bundles after the runs ¦¦ Daily: Rewritten Oct 29 08:10 after both vLLM starts failed: the morning Sol comm… | 204 runs; 954 calls; 636 calls; 27–60 GPU h; 10–15 GPU h; Sol jobs 66878660, 66879362; 954 reviews; 0.6–1.5 A100 h; Sol jobs 66920320, 66928369, 66934413; 163–359 GPU h; compute (daily): Sol: vLLM didn't start, twice. vllm_check 66878660 failed after 24:26, and trackb_qwen3-8b 66879362 after 13:39. Both ended with "Engine core initialization failed", in warmup_kernels inside compile_or_warm_up_model, after the weights loaded. The root-cause line wasn't in the lines copied last night. Command 1 below prints it. The 8 eval parts were removed. Nothing is queued.; Voyager: set A was paused at 01:59 at 130 of 204 runs (the laptop's fans; the load was Spotlight and a VM, not this job). It resumed at 07:58. C11, then C12, follow it automatically under the guard. |  | 0 |  | 2026-10-29_0020_ALL_night-dry-runs-setA-c11-c12.md, 2026-10-29_0810_ALL_hf-generation-for-sol.md, 2026-10-29_1055_ALL_setA-c11-c12-done.md, 2026-10-29_1645_ALL_sol-fixes-and-c13-prereg.md, 2026-10-29_2300_ALL_c14-c15-b15-prereg.md, 2026-10-29_2330_ALL_gate3-raters-handoffs.md, DAILY_2026-10-29.md
2026-10-30 | Fri | Track A: explain and fix | 09:00 Set A Step 10 (F26): replicates: 0.90 [0.76, 1.06] at 15/19/23 on 16 questions not used to find them (31 cuts), and those three are the largest drops (0.43, 0.30, 0.17); Test 2 0.90 [0.85, 0.96]; Step 9 back, unread ¦¦ 09:05 B1's alpha on set A (F27): deployable 0.25 (forced P(W) −7.6, correct hint −4.8), oracle 0.5 (−8.6, −4.3); lower alphas cost a correct hint more than 5 points; not 1, so provenance_gen runs ¦¦ 09:10 Gate 3 interim (F28): met by LoRA (following −10 [−16, −4], accuracy −2 points, hiding −24); an independent one-line instruction does as well (LoRA − prompt_only +3 [−1, +8]); LoRA's false-disclosure candidates rise (+10 [+2, +18]), the instruction's fall (−9); candidate cautionary claim waiting on labels (corrected 10:00: the note isn't what the targets were made with) ¦¦ 10:10 Set A Step 9 pre-registered (Ritik's rule): F12's three heads (L19H31, L23H17, L15H31), hint − control at the answer, followed − resisted, clustered by question; replicates if above 0. Test 2 reference +0.084 [+0.062, +0.105] (inserted + declared alone +0.028, includes 0). Needs set A's step9_reduced.npz from Sol (the lines are in the log). attn_to_hint.py --fixed-heads, --reduce-only ¦¦ 10:35 Set A Step 9 (F32): F12's three heads (fixed in advance) replicate: followed − resisted +0.068 [+0.044, +0.088] on 15 questions (Test 2 +0.084); each head above 0; inserted + declared above 0 here (+0.031); not set A's top heads by mass ¦¦ 10:45 L4, Gate 3's blind label sheets (Ritik's rules): part 1 = LoRA's 147 false-disclosure candidates + 147 matched followed non-candidates from base/prompt_only (106 same question and channel); part 2 = base's 96 and prompt_only's 50 candidates + 146 matched; seed L4-20261030; ~6 h per part per rater; eval.py --label-sheets runs on Sol after the push; kappa reads final-only sheets ¦¦ 11:45 Thread 1 on a second model: Qwen3-8B (thinking on, 36 full-attention layers) Steps 3 and 10 prepared (af2f2fb, 23 CPU tests, not run on a GPU): localize on the 24 puzzles (tool_real, 63 followed runs on sure questions), replicate on the 30 by a fixed rule; Ritik's choices before submission (threshold T, recommended 0.5; match within one layer; the too-few fallback; Step 10's limit); ~1.1 + 2.6–4.3 GPU h ¦¦ 17:15 B1's generation rule fixed before any copy-back (Ritik): chosen alpha − alpha = 1, same HF stack, paired by question; deployable on the inserted-tool channel, oracle on every hint channel; works / ignores tools / costs accuracy (added to cover every outcome) / no effect / worse; B1 vs prompt_only and LoRA beside it, cross-stack | 2.6–4.3 GPU h | F26, F27, F28, F32 | 13 | 8380e56 f369bf6 88415d6 e4e1b1f 65189dc faddef2 df5377d af2f2fb 42a96ab fd1a679 1339638 1b52c43 181dd9d | 2026-10-30_0900_A_setA-step10-replicates.md, 2026-10-30_0905_A_b1-alpha-chosen.md, 2026-10-30_0910_A_gate3-interim.md, 2026-10-30_1010_A_setA-step9-prereg.md, 2026-10-30_1035_A_setA-step9-replicates.md, 2026-10-30_1045_A_l4-label-sheets.md, 2026-10-30_1145_A_qwen8b-mech-prereg.md, 2026-10-30_1715_A_b1-generation-rule.md
2026-10-30 | Fri | Track B: test widely | 04:00 B15 done (1,620 runs, 0 errors; F25): one instruction brings the tool back into the final answer: after a call Thinking names it in 33 of 63 (before 3 of 54, +47 [+30, +64]), Instruct 149 of 162 (before 35, +70 [+59, +81]); the bare letter falls (−47, −61); following doesn't change, nor do correct-tool acceptance or no-hint accuracy: the deference becomes visible, not smaller ¦¦ 09:15 Qwen3-8B, the same weights (F29): thinking on calls the tool 145 vs 35 of 162 and follows the real call +64 [+51, +75] more; pasted and user don't move; Gate 2 clear in both; after a call the answer is bare (138 of 145) | 1,620 runs | F25, F29 | 6 | 60979c4 8380e56 f369bf6 6b2ad02 88415d6 1b52c43 | 2026-10-30_0400_B_b15-results.md, 2026-10-30_0915_B_qwen3-8b-thinking-on-off.md
2026-10-30 | Fri | Track C: multi-agent pipeline | 01:10 C15 done (200 + 100 cases, 0 errors; F24): F18 replicates on 100 fresh items (Olmo −55 [−70, −38], defers; Qwen3 −6 [−15, +4]); redaction restores part of Olmo's check again (+25 [+11, +38]), on MMLU-Pro and puzzles; H23 not supported (+14 [−13, +37]); C14's cheaper rule fails (c1, c2 not confirmed), shipping 4 and 7 wrong of 53 where the checker ships none; F15's bare letter holds ¦¦ 08:50 C16 pre-registered (Ritik approved Oct 30): C15's 100 fresh items, the solver told B15's instruction (--disclose); plus_explanation reviews (the final answer; answer_only shows only the letter, a ruling) against a same-day control on C15's solver and C15's answer_only; two-sided, C11's 20-point margin; dry runs ~700 calls ¦¦ 09:20 C13 (F30): Granite 4.1 30B −5 [−26, +15], Mistral Small 3.2 24B +19 [+10, +30]: neither defers; over six reviewers and four families only Olmo's two do ("Olmo-specific", as pre-registered) ¦¦ 10:25 C17 pre-registered (Ritik approved): C15's saved final answers with one fixed sentence appended, names the lookup tool vs own step-by-step working (same length), against C16's unchanged control; Olmo 3.1 32B and Qwen3 30B Instruct, plus_explanation; main (b) names − own, (a) names − unchanged, two-sided with C11's margin; 400 reviews ¦¦ 10:30 C16 (F31): the solver named the tool after 34 of 55 bad lookups (C15: 5) and still took the wrong letter (54 of 55); the Olmo reviewer seeing that answer corrects 25 against 36 of 53 (−21 [−34, −8]: unclear by the 20-point rule), Qwen3 44 against 44 (no change); descriptive: Olmo −41 where the tool was named, +10 where not. Also at 10:00: F28 corrected (the guide note isn't what the targets were made with), Gate 3's three-part framing and cautionary claim, L4 labels first, the title-question reading (F29), CLAIMS 2.1 family-specific ¦¦ 11:00 C17 (F33): a fixed sentence naming the lookup tool, added to C15's bare answers, doesn't move the Olmo reviewer (names − own working 37 vs 37 of 53, +0 [−11, +11]; names − unchanged +2); Qwen3 no change; C16's drop went with the solver's own explanations (median 353 chars vs 11), not the mention (H33, untested) ¦¦ 17:00 C18 pre-registered (Ritik approved): H33, is the cue the argument? C16's 34 named bad-lookup answers, unchanged vs the tool sentences removed (median 474 → 126 chars), Olmo 3.1 32B and Qwen3 30B Instruct, plus_explanation; main stripped − unchanged, two-sided, C11's margin; C17's own-working version as the length reference; 136 reviews ¦¦ 17:20 C18 (F34): removing C16's sentences that cite the tool restores the Olmo reviewer's check: 25 vs 9 of 34, +47 [+29, +65] (more corrections: "the tool mentions are part of the cue"; H33 not supported); Qwen3 no change; re-review identical to C16; with C17: the cue is the solver's citation of the tool's letter as authority, not a generic label nor the remaining working (H34) ¦¦ 18:05 Track C handed to Shrey: TRACK_C.md final, his plan C19–C24, a portable Sol kit and SOL_SETUP.md, his own Voyager key; th… | 200 + 100 cases; 700 calls; 400 reviews; 136 reviews | F24, F30, F31, F33, F34 | 14 | 8dff157 8380e56 f369bf6 6b2ad02 88415d6 16ef2dc 65189dc e2576ff 4bdfe78 1928820 1339638 cb11212 1b52c43 181dd9d | 2026-10-30_0110_C_c15-results.md, 2026-10-30_0850_C_c16-prereg.md, 2026-10-30_0920_C_c13-granite-mistral.md, 2026-10-30_1025_C_c17-prereg.md, 2026-10-30_1030_C_c16-results.md, 2026-10-30_1100_C_c17-results.md, 2026-10-30_1700_C_c18-prereg.md, 2026-10-30_1720_C_c18-results.md, 2026-10-30_1805_C_handoff-to-shrey.md
2026-10-30 | Fri | Labels | From commits (no session log for this track that day): Gate 3 corrected, the label order, and set A's Step 9 pre-registered before it is read (Oct 30, 10:… ¦ C16 read by its pre-registered rule; the title question; C13's claim (Oct 30, 10:30; FINDINGS F31).… ¦ Daily Oct 30, late morning (10:40): Sol's night read (F26-F30, F28 corrected), C16 run and read (F3… ¦ L4, Gate 3's blind label sheets (Oct 30, 10:45; Ritik's rules). eval.py --label-sheets: part 1 = Lo… ¦ C18 read (FINDINGS F34), B1 generation's rule and L4's order fixed before results (Oct 30, 17:15-17… |  |  | 5 | e4e1b1f 16ef2dc 65189dc df5377d 1339638 | git log
2026-10-30 | Fri | All tracks | 08:45 Sol's night: every job exit 0 (prompt_only, lora, set A Steps 9/10, B1 forced, Qwen3-8B, C13; C13 had its inputs); the QoS re-checked (2 running, 10 submitted, 960 GPU-min: README right); command 4 adjusted (all 10 now, Ritik's order, alpha applied); the push (427f39e..f369bf6); Ritik's decisions (rater asks, C16, B15 wording, the story headline); set A's distance split fixed ¦¦ 17:25 The Gantt sheet (tools/make_gantt.py → docs/progress/GANTT.xlsx, gantt.png, STATUS.md), generated from git, the logs, TODO, PLAN and FINDINGS; 59 of 86 tasks done (A 27/37, B 10/15, C 17/23, labels 2/5, repo 3/6), ~172 h left; milestones; 36 inferred dates ¦¦ 17:40 Repository cleanup: inventory of 521 tracked files by reference scan (134 with no textual reference: tests, files loaded by name, the progress deck's assets, figures, summaries; none stale or irrelevant), so none removed; the Oct 4 bundle to the gitignored results/archive/, an untracked note and 16 .DS_Store files to ~/cse598_trash_20261030/; tools/check_links.py: 0 broken links, 0 missing RUNBOOK scripts ¦¦ 18:00 The supplement (tools/make_supplement.py → docs/paper/supplement/, 46 files): EVIDENCE (34 F entries, 129 CLAIMS numbers checked), PREREGISTRATIONS (23 rules, after-the-fact readings flagged), DEVIATIONS, TRAPS, tables, figures, APPENDIX_OUTLINE; what it caught and was fixed (CLAIMS numbers, F32's rounding), log names set ahead of commits, same-minute starts ¦¦ Daily: The night of Oct 29–30 (no Sol): C14, C15 (F24), B15 (F25) and their numbers; Gate 3 in one command, B2's bias log, the rater guide, the handoffs and bundles; a review of the night's code (two fixes, readings unchanged); six decisions waiting; the morning Sol lines (queue, copy-backs for set A, batch 3, Qwen3-8B and C13, B1's alpha, then the 10 submissions in Ritik's order) | 960 GPU-min; compute (daily): Sol: nothing submitted or changed (Sol was full). The queue as last seen at 21:56 is in command 0 below.; Voyager, under the power guard, 4 in flight, 0 errors: C15: 22:48 – 00:45 (200 solver-and-checker cases, then 600 reviews). B15: 23:57 – 03:44 (1,620 runs). The Mac was on battery from about 23:50 (97% → 57% at 03:44). The guard never paused. It ended at 03:45 with every job done; nothing has run on Voyager since. The battery is at 39% at 06:55: worth plugging in before the next Voyager run. |  | 3 | c0f8141 bbc944d 4fa9c0c | 2026-10-30_0845_ALL_sol-morning-and-decisions.md, 2026-10-30_1725_ALL_gantt.md, 2026-10-30_1740_ALL_cleanup.md, 2026-10-30_1800_ALL_supplement.md, DAILY_2026-10-30.md

## Changes
Date | Time (MST) | Hash | Track (A, B, C, Labels, Setup, ALL; + = several) | Summary (first 120 characters) | Files
2026-10-30 | 17:45 | 181dd9d | A+C | The supplement, generated and tested; what it caught, fixed; the cleanup and handoff logs (Oct 30, 17:40-18:05). tools/… | 58
2026-10-30 | 17:36 | 4fa9c0c | ALL | TODO: A7 (main fast-forwarded and pushed) and R1 (GitHub main has had the Oct 21 Voyager IDs since Oct 29) done. | 1
2026-10-30 | 17:35 | 1b52c43 | A+B+C | A portable Sol kit, so Shrey runs Track C's GPU jobs under his own account (Oct 30). env.sh derives every path from $US… | 39
2026-10-30 | 17:22 | bbc944d | ALL | The Gantt sheet, generated from the repo (Oct 30). tools/make_gantt.py reads git log, the session logs and INDEX, the d… | 5
2026-10-30 | 16:59 | cb11212 | C | Track C handed to Shrey (Oct 30). TRACK_C.md final: the setup; the story in order (F18, F19, F21-F24, F30, F31, F33, F3… | 5
2026-10-30 | 16:56 | c0f8141 | ALL | Cleanup tools (Oct 30): tools/check_links.py checks every internal markdown link in the tracked .md files and every scr… | 3
2026-10-30 | 16:52 | 1339638 | A+C+Labels | C18 read (FINDINGS F34), B1 generation's rule and L4's order fixed before results (Oct 30, 17:15-17:20). C18: removing… | 20
2026-10-30 | 16:48 | fd1a679 | A | Qwen3-8B's replication rule fixed by Ritik before anything is submitted (Oct 30, ~17:10). Replicates: the share of the… | 3
2026-10-30 | 16:45 | 1928820 | C | C18 pre-registered before any call (Oct 30, 17:00; Ritik approved it). H33: is the cue the argument for the wrong lette… | 5
2026-10-30 | 11:04 | 42a96ab | A | Qwen3-8B's Steps 3 and 10 pre-registered, and the evening daily (Oct 30, 11:45-11:50). The localization (3 layers with… | 6
2026-10-30 | 11:02 | af2f2fb | A | Thread 1 on a second model: Steps 3 and 10 for Qwen3-8B with thinking on, prepared, not run (Oct 30). finetune/look/qwe… | 8
2026-10-30 | 10:56 | 4bdfe78 | C | C17 read by its pre-registered rule (Oct 30, 11:00; FINDINGS F33). 400 reviews, 0 errors. A fixed sentence naming the l… | 15
2026-10-30 | 10:37 | df5377d | A+Labels | L4, Gate 3's blind label sheets (Oct 30, 10:45; Ritik's rules). eval.py --label-sheets: part 1 = LoRA's 147 false-discl… | 8
2026-10-30 | 10:28 | e2576ff | C | C17 pre-registered before any call (Oct 30, 10:25; Ritik approved it). Does naming the source cause the Olmo reviewer's… | 5
2026-10-30 | 10:22 | faddef2 | A | Set A's Step 9 read by its pre-registered rule: replicates (Oct 30, 10:35; FINDINGS F32). F12's three heads (L19H31, L2… | 9
2026-10-30 | 09:49 | 65189dc | A+C+Labels | Daily Oct 30, late morning (10:40): Sol's night read (F26-F30, F28 corrected), C16 run and read (F31), the 10 Sol jobs… | 1
2026-10-30 | 09:49 | 16ef2dc | C+Labels | C16 read by its pre-registered rule; the title question; C13's claim (Oct 30, 10:30; FINDINGS F31). C16, 0 errors: the… | 16
2026-10-30 | 09:42 | e4e1b1f | A+Labels | Gate 3 corrected, the label order, and set A's Step 9 pre-registered before it is read (Oct 30, 10:10). F28 and the 09:… | 9
2026-10-30 | 09:03 | 88415d6 | A+B+C | Sol's night read by the rules fixed in advance (Oct 30, 08:45-09:20; FINDINGS F26-F30). Every Oct 29 job ended with exi… | 40
2026-10-30 | 08:50 | 6b2ad02 | B+C | C16 pre-registered before any call (Oct 30, 08:50; Ritik approved it on the Oct 30 daily). C15's 100 fresh items, C4's… | 8
2026-10-30 | 06:56 | f369bf6 | A+B+C | Daily Oct 30 (07:00): the night of Oct 29-30 without Sol. C14, C15 (F24) and B15 (F25) with their numbers; Gate 3 in on… | 2
2026-10-30 | 04:21 | 8380e56 | A+B+C | Corrections from a review of the night's code (Oct 30, 04:15). F25's keyword check was wrong: it said that with no hint… | 8
2026-10-30 | 03:55 | 60979c4 | B | B15 done, read by its pre-registered rules (Oct 30, 04:00; FINDINGS F25). Qwen3 30B Thinking and Instruct, Track B's 54… | 12
2026-10-30 | 00:54 | 8dff157 | C | C15 done, read by its pre-registered rules (Oct 30, 01:10; FINDINGS F24). On 100 fresh items (60 MMLU-Pro outside the e… | 13
2026-10-29 | 22:58 | f688e31 | A+B+C+Labels | Gate 3 in one command, the rater guide, the handoffs and the paper pack with C11-C15 and B15 (Oct 29, 23:30; no calls).… | 13
2026-10-29 | 22:48 | 7e0bae4 | A+B+C | C14 done, C15 and B15 pre-registered before they run (Oct 29, 23:00). C14 (exploratory, no calls; agents/disagreement.p… | 13
2026-10-29 | 21:19 | 427f39e | A | Sol's clone onto GitHub's history, and the import check's vLLM limit (Oct 29, 21:16). Sol's clone came from the Oct 26… | 4
2026-10-29 | 16:33 | 8f9e495 | A | Session log 16:45: Ritik's nine items. ef6afd8 and the vLLM fix pushed; Qwen3-8B 66934413 was a Python 3.11 race on tra… | 8
2026-10-29 | 16:33 | 26b008a | A+C | C13 coded (no runs): a third and fourth reviewer family on Sol, IBM Granite 4.1 30B (ibm-granite/granite-4.1-30b@4fae62… | 11
2026-10-29 | 16:26 | ad7ce06 | A | Two parts of one system on vLLM, safe together (Oct 29). One server log per part, named like its record files (eval/vll… | 3
2026-10-29 | 15:43 | 28d68a4 | A+B | Qwen3-8B 66934413's ImportError was a thread race, not the environment (Oct 29): Track B's runner reached its first fro… | 7
2026-10-29 | 15:34 | 7931b79 | A+B | vLLM on Sol fixed (Oct 29): the server starts with VLLM_USE_FLASHINFER_SAMPLER=0, because vLLM 0.31's sampler warm-up h… | 4
2026-10-29 | 10:50 | ef6afd8 | C | Set A, C11 and C12 done on Voyager (Oct 29, pre-registered in the 00:20 log). Set A: 204 runs, 39 late takeovers on 16… | 10
2026-10-29 | 08:08 | c8d0586 | A+B | Batch 3 and Qwen3-8B on Hugging Face generation (vLLM failed to start on Sol twice, Oct 29: S2 66878660 and Qwen3-8B 66… | 32
2026-10-29 | 00:31 | 0bd2241 | A | B1 and B2 coded (no runs): provenance-scaled attention at inference (finetune/provenance.py: log(alpha) added to the at… | 14
2026-10-29 | 00:25 | 6aabe46 | A+C | Night of Oct 29, before the runs: set A (finetune/setA.py: the 34 validation questions, in neither training nor Test 2,… | 27
2026-10-29 | 00:09 | 487d47d | A+B+C | Attribution made accurate: every session log's By line, every next-step line and every past-work owner in TODO is Ritik… | 18
2026-10-28 | 23:29 | 5cdc2d6 | A+B+C | Docs name people, not tools: every author, owner and doer credited to a tool is now the track's owner (Track A Ritik, T… | 20
2026-10-28 | 23:19 | 28e93c4 | C | C10 (FINDINGS F21): committing to its own answer first doesn't protect the reviewer's check. 23:06-23:16, 636 calls, 0… | 11
2026-10-28 | 23:06 | 84151ab | A+C | F20's tags check and C10 (commit first), before its run. Tags check from S7's files (no jobs): lora_tags minus lora on… | 15
2026-10-28 | 22:46 | 3cf2044 | A+C | S7 and C9 reported. Training against base (FINDINGS F20; S7 66865939, 0:37:09, all four versions, epoch 2; 156 validati… | 19
2026-10-28 | 21:51 | c140107 | A+B+C+Labels | vllm_check 66862780 refused at the preflight on --mm-processor-device (a cuda choice on sg018, an option no command use… | 22
2026-10-28 | 18:23 | 84e6acb | A+B+C+Labels | Voyager done: Olmo 3 7B Think (FINDINGS F17: Gate 2 clear, pasted +32 [+22, +42], injected +21 [+13, +30]; its final an… | 29
2026-10-28 | 12:20 | bb8399a | A+B+C+Labels | Sol batch 2: lora and tags done (both epoch 2; validation loss 0.18537 and 0.21401; 3.41 h and 2.81 h, 5-7% under the r… | 15
2026-10-28 | 07:03 | 9199756 | B+C | Daily log Oct 28 (the night, 23:08-07:00), copied to LATEST: Qwen3 30B Thinking and Instruct done (Gate 2 clear for bot… | 7
2026-10-28 | 05:45 | b104426 | B+C | Session log time corrected to 05:45 (written at 05:43, not 06:00); RUNBOOK 19: the 32B reviewer, C4 under the guard, --… | 7
2026-10-28 | 05:43 | 8fb6243 | B+C | Track B Qwen3 30B Instruct final (810 runs, FINDINGS F16): following user 1 of 162, pasted 35 of 162, real call 147 of… | 14
2026-10-28 | 03:25 | 7ac2dc2 | C | handoff/TRACK_C: C4 running (318 cases, since 03:13 under a second guard), C5 and the kind / set split in --summary, ex… | 1
2026-10-28 | 03:24 | 8aea482 | B | trackB_report: thinking minus not (Qwen3 30B Thinking vs Instruct; Qwen3-8B thinking on vs off), following per channel… | 2
2026-10-28 | 03:22 | 421c49d | C | run_team --summary --cases: the C4 summary also per Track B kind (steered / matched) and per kind x question set, joine… | 2
2026-10-28 | 03:21 | b404516 | B | Track B Qwen3 30B Thinking final (810 runs, FINDINGS F15): following user 3 of 162, pasted 59 of 162, real call 54 of 1… | 11
2026-10-28 | 00:42 | b9e648d | A+B | get_qwen8b: small files checked by the Hub's git blob id (weights and tokenizer.json by sha256), as the real Hub metada… | 3
2026-10-28 | 00:40 | 861b17a | B | Session log 2026-10-28 00:45 (B): Track B interim table (Qwen3 30B Thinking, ~1 run per question on 54): following user… | 3
2026-10-28 | 00:39 | e0b6870 | B+C | Overnight Oct 28 (2): one failed Voyager guard pauses all Voyager work (client.py writes logs/voyager_halted; every pro… | 10
2026-10-28 | 00:32 | 49f1f76 | A+B+C | Overnight Oct 28 (1): Track C's second reviewer is Olmo 3 32B Instruct (decision 5): A27, Voyager's olmo3-32b instruct… | 28
2026-10-28 | 00:02 | 1c66f33 | A+B | vLLM's option list on the GPU node, not the CPU (Oct 28: the CUDA build's vllm serve --help=all fails on a CPU node, 'F… | 12
2026-10-27 | 23:54 | aacf296 | A+B | Oct 28: the class QoS only; training ready (data checks, S1 refit, batch 2); Qwen3-8B moves to Sol; Voyager models in s… | 34
2026-10-27 | 23:11 | 8125f48 | A+B | Session log 2026-10-27 23:08 (ALL): the first Sol jobs fixed (submit.sh; S2 failed on --disable-log-requests, now check… | 5
2026-10-27 | 23:07 | 79ace0b | A | Sol S2 fix: vLLM 0.31.0 has no --disable-log-requests (request logging is off by default); removed from every server co… | 10
2026-10-27 | 21:11 | cbbd936 | A | Sol: submit.sh never silent, dependencies checked; vLLM in its own environment. submit.sh: a job script without a GPU l… | 15
2026-10-27 | 15:17 | 8d8e206 | B | Track B, Oct 27 decisions 2 and 3. One budget for every open model: 32,768 tokens, prompt (counted with the model's own… | 10
2026-10-27 | 15:02 | a0e5527 | C | Session log 2026-10-27 15:05 (C): C1, the live team on 5 items (checker caught 3 of 3 bad lookups, no false alarm; revi… | 4
2026-10-27 | 15:01 | 6ca141a | B+C | Track C after C1 (5 items): the summary adds the reviewer alone (corrects a wrong solver answer / keeps a right one / n… | 7
2026-10-27 | 14:55 | be8f028 | B+C | export_summaries.py also copies Track B's and Track C's numbers-only reports (trackB_report.json, template_check.jsonl,… | 1
2026-10-27 | 14:54 | 35f7c19 | B+Labels | Code README: Oct 27 files (Track B report, template check, canaries, label kit, handoff bundles, Steps 11-13), 340 tests | 1
2026-10-27 | 14:54 | 19d1b75 | Labels | OVERVIEW and PLAN brought up to date (Oct 27 14:55): status per track after today's runs and code, the code map's new f… | 3
2026-10-27 | 14:50 | 18cdcfa | A | Figures #1 (pinned panel) and #4 (A22, A23): finetune/look/plot_figures.py draws, from the tracked summaries only, Step… | 8
2026-10-27 | 13:59 | 39c171d | ALL | Session log 2026-10-27 14:00 (ALL): everything paused for an hour; runs stopped cleanly, resumable | 3
2026-10-27 | 13:58 | 91689dd | B | Track B table (B14) and the Gate 2 question (B9): progress/trackB_report.py, from the saved runs (no calls): per model… | 2
2026-10-27 | 13:57 | e4b2206 | B+C | Docs: last-updated times corrected to the clock (13:55, 13:57) | 3
2026-10-27 | 13:57 | d534d19 | B+C | Handoff docs (H2, H3), drafts kept current until Nov 3: docs/handoff/TRACK_B.md for Arsha and TRACK_C.md for Shrey: wha… | 3
2026-10-27 | 13:56 | 957590b | A | train.py docstring: the export runs at the end of the last epoch | 1
2026-10-27 | 13:56 | de6affa | A | train.py exports the chosen epoch (out/final/) when the last epoch ends, so evaluation can start without a separate ste… | 2
2026-10-27 | 13:55 | 1ad0a65 | B+C+Labels | RUNBOOK brought up to date (Oct 27 14:10): Steps 6-7 done; Steps 11-13 commands (rsync of inputs, setup_vllm, timing, v… | 1
2026-10-27 | 13:54 | 87f3357 | B+Labels | tools/make_handoff_bundle.py (H4): a tar.gz per track of its gitignored results (A: results/trackA, finetune/data; B: r… | 2
2026-10-27 | 13:54 | d905f1b | ALL | Session log 2026-10-27 14:00 (ALL): the history rewrite of trackA-nosol with its safeguards, local main fast-forwarded,… | 3
2026-10-27 | 13:53 | ebc8dde | A+B+Labels | TODO: statuses after Oct 27 (Steps 6-7 done and assembled; rewrite of trackA-nosol done, main waits on its plan; Steps… | 1
2026-10-27 | 13:48 | 4ad4e85 | A | Session log 2026-10-27 13:55 (A): Steps 6-7 final counts (251 kept of 530 [43, 52%]; Step 7 targets per channel; length… | 3
2026-10-27 | 13:47 | 834c0f3 | A | Steps 6-7 done (251 kept of 530; 1,196 examples assembled: 1,040 train from 217 questions, 156 validation from 34; 120… | 15
2026-10-27 | 13:46 | f8149e4 | Labels | Labels: the kit and the 10 replacement rows (L1, L2). tools/label_kit.py build (no calls): the 10 queue rows without te… | 6
2026-10-27 | 13:41 | dda0d6a | B | Identity canary for olmo3-7b-instruct (Track C's second reviewer; 319 prompt tokens; passed on the next call). Its serv… | 2
2026-10-27 | 13:39 | 94cfc4d | C | Track C: run_team.py appends to gitignored results/trackC/ (never rewrites; results/scope/ keeps the Oct 4 runs) and re… | 3
2026-10-27 | 13:35 | fc708d7 | B | Session log 2026-10-27 13:05 (B): Track B smoke tests 15 of 15, served-template check (gap 0 except Qwen3's tool spec,… | 3
2026-10-27 | 13:01 | 3848f77 | A | Track A Sol jobs for Steps 11-13 (S1-S6, E1-E6): timing, vllm_check, train, eval .sbatch (class QoS, 1 A100, --signal=B… | 11
2026-10-27 | 12:55 | 41506a3 | A | Sol kit QoS checks (Oct 27): accounts.conf lists the accounts Track A may use with partition, QoS and the QoS limits (t… | 4
2026-10-27 | 12:51 | 81415f7 | B | Track B: jobs go repeat-major across the models of one call (Ollama's thinking on and off interleave, so a partial run… | 3
2026-10-27 | 12:51 | 8cf0453 | A | Track A Step 13: finetune/eval.py. 31 runs per held-out question (930 per system): 6 held-out wordings x wrong hint x 3… | 3
2026-10-27 | 12:47 | df32ccb | A | Track A Step 12: finetune/generate.py. complete_fns for continuation.continue_to_answer: a local vLLM server's /v1/comp… | 2
2026-10-27 | 12:44 | c7c953d | A | Track A Step 11: finetune/train.py. Versions lora, tags (base frozen), lora_tags, and lora_attn3 (the fourth: LoRA on t… | 2
2026-10-27 | 12:39 | 0584528 | B | Track B: --thinking on¦off keeps one setting (Ollama's qwen3:8b has both); the Ollama adapter waits up to an hour for a… | 3
2026-10-27 | 12:38 | 2095782 | B | Identity-canary references for qwen3-30b-a3b-thinking-2507 (293 prompt tokens) and qwen3-30b-a3b-instruct-2507 (291), e… | 3
2026-10-27 | 12:22 | f106ff9 | B | Track B, ready for Voyager: run_trackB.py gets --model (repeatable), jobs repeat by repeat (--limit 5 = one question in… | 5
2026-10-27 | 12:13 | 8ce47fd | ALL | History rewrite, scoped and backed up (Oct 27 conditions): untrack_produced.py --not-in BRANCH leaves the commits of lo… | 3
2026-10-27 | 12:08 | f4400da | A | Plan for Oct 27-Nov 3 recorded. Owners: Ritik runs Tracks A, B and C until Nov 3, then B goes to Arsha and C to Shrey (… | 6
2026-10-27 | 10:08 | b59d145 | ALL | Session log: catch-up on the whole project (2026-10-27 10:10 MST); docs/sessions/ with LATEST.md and INDEX.md | 3
2026-10-27 | 10:07 | 256e1b3 | A | Docs brought up to date (Oct 27) and the open-work audit. New: docs/TODO.md (every open item across Tracks A, B, C, lab… | 9
2026-10-27 | 09:53 | c2a95b0 | A | Sol scripts call the project environment's Python by full path: env.sh sets TRACKA_PY=/scratch/ragarw68/envs/olmo/bin/p… | 4
2026-10-27 | 09:51 | c29f29f | A | Track A Step 9 matched onsets recorded (F14, T9). At every lead onset after the first fifth, attention to the hint (ful… | 9
2026-10-26 | 19:26 | 679df2e | A | Track A Step 9 follow-up results and a matched redo. Full-attention layers: tool - user -8.1e-3 [-1.0e-2, -6.1e-3] (hin… | 23
2026-10-26 | 15:15 | 53b5a35 | A | Track A Steps 8-10 results from Sol. Step 8: the Oct 26 rule fails (a) at 4 positions with gaps 0.113-0.140 ((b) and (c… | 22
2026-10-26 | 13:31 | 38ef97f | A | Data stays off GitHub: produced folders gitignored (results/trackA¦B¦C, finetune/data, the canary log, GPQA files); num… | 53
2026-10-26 | 10:24 | 7ad8cf6 | A | Track A: Step 8 rule fixed before the result (same checkpoint if (a) no first-2,047 mismatch outside near-ties in bf16… | 9
2026-10-26 | 09:57 | e2cbe93 | A | Track A Step 10 on Sol: patching.py (Step 4's 21 cases; cuts (i) before the first hint mention, 19 cases, and (ii) at t… | 6
2026-10-26 | 09:51 | a6085d0 | A | Track A Step 9 on Sol: attn_to_hint.py (one forward pass per hinted Step 2b run; a registered attention implementation… | 5
2026-10-26 | 09:44 | 1de71bb | A | Track A Step 8 on Sol: checkpoint_check.py (local bf16 + fp32 forward over Step 1's, the Oct 21 and the canary echo tex… | 6
2026-10-26 | 09:39 | 0bcf60e | A | Track A Sol kit, item 1: setup_env.sh (torch 2.14.1+cu130 and pinned packages into /scratch/ragarw68/envs/olmo), smoke.… | 15
2026-10-25 | 12:33 | 69a681b | A | Track A steps 6+7 setup: instruction rule narrowed to the guiding note's own phrases; final-answer stance by keyword; h… | 8
2026-10-25 | 00:43 | a32096e | A | Track A step 7 prefill pilot: 28 of 30 records get a prefill target (note pilot: 18 of 30), 1.43 samples per record, 93… | 0
2026-10-25 | 00:31 | 9e67c0e | A | Track A: prefill targets (reasoning and final-answer openers from 10 paraphrases, no instruction to quote; reject reaso… | 12
2026-10-24 | 21:29 | 4b31f1c | A | Track A step 7 pilot: 30 records (5 kept questions x 3 channels x wrong/correct), 76 samples; a guided sample passes fo… | 2
2026-10-24 | 21:00 | 3a63cf4 | A | Track A step 6 pilot: 10 questions x 3 no-hint runs; 5 kept (3 disagree, 1 agree on a wrong answer, 1 cut off at the co… | 0
2026-10-24 | 20:34 | 39fe64c | A | Test: the written dataset's checks follow Step 5 (training empty until Step 6, correct-hint records on purpose; held-ou… | 1
2026-10-24 | 20:32 | 01add40 | A | Track A steps 6-7 code: training pool (600 questions, prefix-stable, 0 overlap), no-hint runner (pinned format, continu… | 8
2026-10-24 | 20:24 | e3dae86 | A | Before Step 6: length audit split by channel and tool rounds (a run's final sequence counted once; continuations are no… | 3
2026-10-24 | 19:27 | 8c41730 | A | Track A step 5: dataset rules (all-correct target rule, no fallback; old majority rule behind a flag; correct-hint reco… | 4
2026-10-24 | 19:21 | aa1c13c | A | Track A: one continuation for every rerun (finetune/continuation.py). A tool call in the final answer is answered as ru… | 5
2026-10-24 | 19:17 | c799a33 | A | Step 4 report: re-mentions in continuations that end on the hint letter (hint arm 34 of 44, control 46 of 51, unedited… | 2
2026-10-24 | 19:16 | f9e5037 | A | Re-score every saved result with the fixed parser (no calls): 1 letter changes, a Step 4 hint-arm continuation (no answ… | 3
2026-10-24 | 19:13 | 66c55ef | A | Parser: read 'Answer' wrapped in markdown bold ('Answer: D', 'the answer is E'); found in a Step 4 continuation. Saved… | 2
2026-10-24 | 18:58 | b880905 | A | Track A step 4 done: 19 cases, 209 calls. Forced answer at the cut back to the own answer: hint 7 of 19, control 1 of 1… | 1
2026-10-24 | 18:17 | de6888e | A | Before Step 4, 2(a) matched: onsets of the hint's lead after the first fifth, permanent (takeover) vs temporary; own an… | 2
2026-10-24 | 18:14 | 82260cd | A | Step 4: unedited arm (3 continuations from the original cut); token cap per case = the original's remaining budget (16,… | 2
2026-10-24 | 18:09 | 06e7599 | A | Track A storage: files with full replies are gzip by default (base_format 33.8 -> 7.2 MB with a one-row-per-record base… | 10
2026-10-24 | 17:57 | 9fda7fc | A | Track A step 4: deletion test script (hint mentions vs length-matched control before the takeover cut; forced answer +… | 3
2026-10-24 | 17:53 | 3d95fc1 | A | Before Step 4: concentration of followed runs on sure questions; late takeovers vs resisted runs' closest approaches (o… | 2
2026-10-24 | 17:51 | 5f01a2b | A | Step 3 storage: per-probe records move to takeover_probes.jsonl.gz (15.7 MB, same 228 records, checked) with a one-row-… | 6
2026-10-24 | 17:41 | b4ff76d | A | Track A step 3 done: 219 runs, 137,143 probes (early answering, Lanham et al. 2023); report adds counts, k=0 starting p… | 6
2026-10-24 | 17:41 | 878d80b | ALL | Canary: no reply is not a verdict. Requests pause, the canary retries every 2 minutes, the run resumes when it passes,… | 5
2026-10-24 | 13:06 | 5007dd4 | A | Step 3 report and figures: resisted runs show whether the hint leads before any reasoning and where it last leads; figu… | 2
2026-10-22 | 01:42 | 3856f48 | A | Track A step 2b done: 240 of 240 runs ok through the new route; 93 continued past 16,000 tokens (91 finished, 2 cut off… | 0
2026-10-22 | 01:36 | a4da5ac | A | Step 2b report: differences as a bootstrap clustered by question (common.boot_diff), declared minus default arm; cut-of… | 3
2026-10-22 | 01:33 | 57a79a1 | A | Track A step 3: a probe without log-probs fails its run; a curve with a gap is not done and is probed again | 2
2026-10-22 | 01:31 | e4ff278 | A | Track A step 2b: 92 cut-off runs continued (90 finished); fix two run faults: a call quoted inside the reasoning trippe… | 4
2026-10-22 | 00:07 | a6d7bd0 | A | Track A step 2b: main run done through the new route (239 of 240 ok; 1 ConnectionResetError being rerun); cut-off runs… | 0
2026-10-22 | 00:06 | 06608eb | A | Track A step 3 pilot: Voyager refuses a list of prompts (HTTP 400), so one probe per request; 78 probes at 0.38 s media… | 2
2026-10-21 | 23:28 | 515e8d6 | A | Track A step 2b report: cut-offs at 16,000 tokens, continued to the context, and still cut off | 1
2026-10-21 | 23:27 | 1b5f871 | A | Track A step 3: takeover curve (probe after every sentence, one request per probe, last probe first for the prefix cach… | 5
2026-10-21 | 23:01 | fbd8db5 | A | Client: a list of prompts in one /v1/completions request keeps each prompt's own text, log-probs and finish (for Step 3… | 2
2026-10-21 | 22:54 | 4eba10e | A | Track A step 2b: continue cut-off replies up to the 65,536-token context (automatic for new runs; --extend for saved on… | 4
2026-10-21 | 17:21 | 244bcb1 | A | Track A step 2b: resume through the new Voyager route (guards on, old-route runs rerun and superseded, not_run retries)… | 4
2026-10-21 | 16:32 | a0c6066 | A | Voyager ID change (Oct 21): routing, prompt-length and identity checks (7 calls); 11 Step 2b runs saved before the swit… | 1
2026-10-21 | 13:57 | 06b45ed | A | Track A step 2b smoke test: 3 calls, all checks passed | 0
2026-10-21 | 13:55 | e3bbb72 | A | Track A step 2b: declared-functions arm, contradiction count, smoke test | 6
2026-10-21 | 13:43 | 96f536a | A | Track A step 2b: base-model runner in the pinned format (dry run only); template revision scan (no calls) | 3
2026-10-21 | 13:40 | b225b50 | A | Track A step 2: pinned Olmo Think format, tool_injected, render-based source tags | 12
2026-10-21 | 13:17 | c1f312e | A | Track A step 1 results: Voyager capability probe on olmo3-7b-think (8 calls + 1 repeated 400) | 1
2026-10-21 | 17:20 | 019959c | B+C | Voyager model IDs changed (Oct 21): one mapping, guards in the shared client | 13
2026-10-21 | 13:09 | 50bacba | A | Track A step 1: Voyager capability probe; client: extra fields, /v1/completions, logprobs, error detail | 7
2026-10-21 | 13:01 | 15e0047 | ALL | Updated ppt | 2
2026-10-20 | 13:35 | 955ebbe | A+B+C | Docs: one overview, one plan; 15 docs merged and removed | 28
2026-10-06 | 12:54 | 0ad378a | Setup | updated ppt | 2
2026-10-05 | 23:48 | adc0518 | Setup | Final demo: the presentation's runs at /, first playground removed | 40
2026-10-05 | 23:29 | d556782 | Setup | Demo v2: one column per hint, presentation numbers, charts page | 25
2026-10-05 | 22:39 | 70f9994 | Setup | Demo v2: the presentation's examples with exactly its runs | 29
2026-10-05 | 15:21 | 8d14f58 | Setup | Updated ppt | 1
2026-10-05 | 15:17 | c0581b8 | Setup | Engineering example (Case 6) renamed and moved up; tool-result wording; reasoning opens at the first mention | 22
2026-10-05 | 14:02 | 1edfd70 | Setup | Updated UIv2 | 1
2026-10-05 | 13:37 | 2034153 | Setup | Playground back to the sidebar + center layout, presentation-ready | 22
2026-10-05 | 13:17 | 58d149e | Setup | Small-question examples and a simpler, visual playground | 29
2026-10-04 | 23:43 | cdef34a | Setup | Ui Demo updates | 1
2026-10-04 | 23:33 | f05b4f4 | Setup | Interactive wrong-hint playground | 21
2026-10-04 | 23:15 | 2f9cb0a | Setup | Add v3 of the progress presentation deck | 1
2026-10-04 | 23:04 | fb418c0 | Setup | Merge branch 'demo-ui' into main | 0
2026-10-04 | 22:58 | 5b23d86 | Setup | Demo UI for the progress presentation | 19
2026-10-04 | 22:20 | 338f4b6 | Setup | Scope update part 2: docs for the new scope, plan, tracks and budget | 23
2026-10-04 | 22:13 | b526d3a | Setup | Scope update part 3: provider adapters, budget guard, real tool calls, Track B/C/A scaffolds | 39
2026-10-04 | 22:02 | 5ac498b | Setup | Scope update part 1: private/final mention overlap and Test 2 combined counts | 2
2026-10-04 | 19:20 | 8941bb9 | Setup | Add tool-hint, reviewer and leak results to the progress deck | 2
2026-10-04 | 19:13 | 3517b2b | Setup | Restore .gitignore rules and .env.example | 2
2026-10-04 | 19:12 | 76c3c2b | Setup | Add progress-round experiments, figures and notes | 80
2026-10-04 | 18:56 | 227be96 | Setup | updated gitignore | 1
2026-10-04 | 18:55 | 13bf5ca | Setup | added current ppt | 4
2026-10-04 | 14:49 | 566d633 | Setup | Address review: answered-only cue rates, guard tie rule, hint-in-text caveat | 15
2026-10-04 | 14:43 | 960ca6f | Setup | Experiment B results, figures F1-F9, evidence viewer, screenshots, docs | 37
2026-10-04 | 14:05 | a737ef0 | Setup | Experiment B: no-cue screen on 30 MMLU-Pro items (180 calls, 0 errors) | 5
2026-10-04 | 13:58 | 1a140b7 | Setup | Truncation sweep (3c): leak follows request mode, not the cap | 6
2026-10-04 | 13:47 | 712b0df | Setup | Experiment A: reviewer demo on real cue-steered answers (demo, n=5+6) | 27
2026-10-04 | 13:17 | 3672241 | Setup | Progress run phase 0-1: shared helpers, timing run, model manifest | 19
2026-10-04 | 10:15 | 52e246f | Setup | Rework progress slides for first-time viewers | 2
2026-10-02 | 13:51 | e50f343 | Setup | Final progress-round results and plain-language slides | 7
2026-10-02 | 12:55 | 69ffa33 | Setup | Add hint-acknowledgment harness, results, and progress deck | 24

## Progress
Track | Tasks | Done | In progress | Planned | Blocked | Done % (by count) | With a time estimate | Without one | Hours done | Hours estimated | Done % (weighted by time) | Remaining hours | Remaining: work | Remaining: GPU | Remaining: Voyager | Open tasks without an estimate
Track A: explain and fix | 37 | 28 | 3 | 5 | 1 | 75.7 | 22 | 15 | 24.53 | 84.71 | 29 | 60.17 | 8 | 52.17 | 0 | 1
Track B: test widely | 15 | 10 | 1 | 1 | 3 | 66.7 | 12 | 3 | 26.25 | 27.75 | 94.6 | 1.5 | 1.5 | 0 | 0 | 2
Track C: multi-agent pipeline | 23 | 17 | 0 | 6 | 0 | 73.9 | 18 | 5 | 22.73 | 118.73 | 19.1 | 96 | 96 | 0 | 0 | 0
Labels | 5 | 2 | 0 | 0 | 3 | 40 | 5 | 0 | 2 | 13.5 | 14.8 | 11.5 | 11.5 | 0 | 0 | 0
Repo, docs and handoff | 6 | 4 | 1 | 1 | 0 | 66.7 | 5 | 1 | 3.17 | 5.2 | 60.9 | 2.03 | 2.03 | 0 | 0 | 0
All | 86 | 61 | 5 | 13 | 7 | 70.9 | 62 | 24 | 78.68 | 249.89 | 31.5 | 171.2 | 119.03 | 52.17 | 0 | 3
Counted: TODO's task rows and items named in session logs or commits that TODO doesn't list yet; not counted: gates, handoffs, presentations, the report (milestones), standing duties (H5, D1, D2, D3) and the history rows from OVERVIEW.
Weighted: TODO's Time column (working time for code and docs, GPU or Voyager time for runs; ranges at their midpoint, 1 day = 8 h, per-rater or per-part figures once; the Needs column's hours where Time has none); rows with no hours in either have no estimate.
Read as in progress (no status word in TODO): B9.
Blocked because 'Blocked by' names an outside step (push, rater, keys, decision): A37, L4.
Not in TODO yet (from session logs or commits): none.

## Remaining
Due | ID | Task | Track | Owner | Start | Estimate (TODO) | Hours | Depends on | Status | Due date from | Kind
2026-11-03 | H2 | docs/handoff/TRACK_B.md, for Arsha: what's done, results (FINDINGS links), how to run each step (RUNBOOK), open items, inherited decisions, traps; current all… | Repo, docs and handoff | Ritik | 2026-10-27 | 2 h | 2 |  | in progress | TODO row | task
2026-11-03 | Handoff B | Track B to Arsha | Milestones: gates, handoffs, presentations, report | Arsha | 2026-11-03 |  |  |  | planned | the owner rule | milestone
2026-11-05 | C19 | H34: is an authority claim the cue? C15's bare answers + an answer-key citation sentence vs an own-working sentence of the same length; Olmo 3.1 32B and Qwen3… | Track C: multi-agent pipeline | Shrey (from Oct 30) | 2026-10-30 | ~400 reviews; 1 day | 8 |  | planned | TODO row | task
2026-11-08 | B9 | The Gate 2 question: is the tool-vs-user gap still clear with 3 runs per question and more models? Answered as soon as the data allows | Track B: test widely | Arsha (from Nov 3) | 2026-10-27 |  |  | B14 | in progress | Gate 2 (PLAN) | task
2026-11-08 | Gate 2 | Gate 2: the tool-vs-user gap (B9) and the hand labels with kappa (L3) | Milestones: gates, handoffs, presentations, report | everyone | 2026-11-08 |  |  | B9, L3 | planned | PLAN | milestone
2026-11-08 | L3 | Label the queue, two raters; Cohen's kappa per channel; under 0.6, tighten the guide and label a fresh batch | Labels | Ritik | not in the repo | 3–4 h per rater | 3.5 | raters | blocked | Gate 2 (PLAN) | task
2026-11-09 | A16 | Evaluate base, prompt-only and the trained versions on Sol (batch 3) | Track A: explain and fix | Ritik | 2026-10-26 | ~7 GPU h per system (vLLM, measured on base) | 7 |  | in progress | before A18 (it waits on it) (inferred) | task
2026-11-09 | A19 | Fourth version (S6, E6): LoRA on the attention of layers 15, 19, 23 only; included, scheduled last, dropped if E1–E5 aren't done by Nov 9 | Track A: explain and fix | Ritik | 2026-10-26 | 6–16 GPU h | 11 | A16 | planned | TODO row | task
2026-11-09 | C20 | A structural fix: the trace withheld, or a blind first review that only reports disagreement; pipelines on C15's items against the checker (TRACK_C §8, 2) | Track C: multi-agent pipeline | Shrey (from Oct 30) | 2026-10-30 | ~800 reviews; 2 days | 16 |  | planned | TODO row | task
2026-11-09 | A18 | Look-inside rerun on the best version (L1): Step 10 drops at 15/19/23; heads L19H31, L23H17, L15H31: drop, or stay while the answer stops following | Track A: explain and fix | Ritik | 2026-11-04 | 4–10 GPU h | 7 | A16 | planned | PLAN timeline (Nov 4–Nov 9): look inside the best version (L1) | task
2026-11-13 | C21 | Items the solver can't answer without the tool, where the checker's floor rises (fresh MMLU-Pro outside the 30) (TRACK_C §8, 3) | Track C: multi-agent pipeline | Shrey (from Oct 30) | 2026-10-30 | ~600 calls; 2 days | 16 |  | planned | TODO row | task
2026-11-17 | C22 | Another solver model (Olmo 3 7B Think or Qwen3 30B Instruct's steered cases), C4's design (TRACK_C §8, 4) | Track C: multi-agent pipeline | Shrey (from Oct 30) | 2026-10-30 | ~2,000 calls; 3 days | 24 |  | planned | TODO row | task
2026-11-19 | C23 | A pre-registered set of reviewer wordings on C4's cases, Olmo 3.1 32B (TRACK_C §8, 5) | Track C: multi-agent pipeline | Shrey (from Oct 30) | 2026-10-30 | ~1,500 reviews; 2 days | 16 |  | planned | TODO row | task
2026-11-20 | A13 | First Sol jobs: setup_vllm (envs/olmo-vllm), S1 the timing run, S2 the vLLM check | Track A: explain and fix | Ritik | 2026-10-25 | 150 GPU-min | 2.5 | Ritik submits | in progress | PLAN: all evaluation done by (inferred) | task
2026-11-20 | L4 | Gate 3's labeling sheets (Ritik, Oct 30: blind, no system or candidate marks; no part only candidates): part 1 = LoRA's 147 false-disclosure candidates + 147 m… | Labels | Ritik | 2026-10-25 | ~6 h per part per rater (294 and 292 rows, ~1¼ min a row) | 6 | A16; the push | blocked | before A17 (it waits on it) (inferred) | task
2026-11-20 | A30 | B1, provenance-scaled attention at inference (finetune/provenance.py): the forced-answer job on set A's cuts (chooses alpha on set A), then generation on the 3… | Track A: explain and fix | Ritik | 2026-10-29 | P1 0.25–0.5, P2 11–23 GPU h | 17.38 | A29 | in progress | PLAN: all evaluation done by (inferred) | task
2026-11-20 | A31 | B2, provenance-gated attention bias (versions gate3, lora_attn3_gate in train.py): a learned per-head bias on tool-tagged keys in 15/19/23, zero-initialized; L… | Track A: explain and fix | Ritik | 2026-10-29 | ~2.75 GPU h each | 2.75 | batch 3's order | planned | PLAN: all evaluation done by (inferred) | task
2026-11-20 | A37 | Thread 1 on a second model (Ritik, Oct 30): Qwen3-8B thinking on, Step 3 and Step 10 on Track B's runs; localize on the 24 pilot puzzles (tool_real), replicate… | Track A: explain and fix | Ritik | 2026-10-30 |  | 4.55 | the push; the 10 jobs | blocked | PLAN: all evaluation done by (inferred) | task
2026-11-20 | A17 | Step 13 analysis: 4 measures, hiding check, false-disclosure check, measure 4 on hand-label categories, "tags help more on the inserted tool turn than the past… | Track A: explain and fix | Ritik | 2026-11-10 | 1 day | 8 | A16, L4 | planned | PLAN timeline (Nov 10–Nov 20): Step 13 analysis | task
2026-11-22 | C24 | Thread 2's paper figures and tables (TRACK_C §8, 6) | Track C: multi-agent pipeline | Shrey (from Oct 30) | 2026-10-30 | 2 days | 16 |  | planned | TODO row | task
2026-11-22 | Gate 3 | Gate 3: a trained version follows fewer wrong hints, accuracy within 5 points, hiding check not up | Milestones: gates, handoffs, presentations, report | everyone | 2026-11-22 |  |  | A17 | planned | PLAN | milestone
2026-11-29 | A21 | Hand the best version to Tracks B and C (week 15) | Track A: explain and fix | Ritik | 2026-11-23 |  |  | A16 | planned | PLAN timeline (Nov 23–Nov 29): Hand the best version to B and C | task
2026-11-29 | Draft report | Draft report (exact day not in the repo) | Milestones: gates, handoffs, presentations, report | Ritik | 2026-11-23 |  |  |  | planned | PLAN timeline window (its end) (inferred) | window
2026-12-06 | Final presentation | Final presentation (week 16) (exact day not in the repo) | Milestones: gates, handoffs, presentations, report | everyone | 2026-11-30 |  |  |  | planned | PLAN timeline window (its end) (inferred) | window
2026-12-12 | Final report | Final report (exact day not in the repo) | Milestones: gates, handoffs, presentations, report | Ritik | 2026-12-07 |  |  |  | planned | PLAN timeline window (its end) (inferred) | window
not in the repo | B1 | Closed-provider keys: a real OpenAI key (the current one is the Voyager key), Anthropic, xAI | Track B: test widely | Arsha (from Nov 3) | 2026-10-05 |  |  | keys | blocked | not in the repo | task
not in the repo | B3 | Closed-model smoke tests (run_trackB.py --run --only-provider X --limit 1) | Track B: test widely | Arsha (from Nov 3) | 2026-10-25 | 15 min | 0.25 | B1, "go" (paid) | blocked | not in the repo | task
not in the repo | R2 | The pre-push hook is installed only on this Mac; each teammate installs it (RUNBOOK, repo hygiene) | Repo, docs and handoff | Ritik | 2026-10-26 | 2 min | 0.03 |  | planned | not in the repo | task
not in the repo | L5 | Track B labeling batch (tools/label_kit.py trackb), labeled in order: group 1, Qwen3 Thinking's runs that followed after a real call or with the pasted block (… | Labels | Ritik | 2026-10-28 | group 1: ~2 h per rater | 2 | L3 | blocked | not in the repo | task
not in the repo | B2 | Is Claude Haiku 4.5 still served? Swap in its replacement if not (Haiku 5.5 needs an adapter change) | Track B: test widely | Arsha (from Nov 3) | not in the repo | 15 min | 0.25 | B1 | planned | not in the repo | task
not in the repo | B6 | GPQA Diamond: export to data/gpqa_diamond.jsonl (gitignored); nothing from it in any doc or tracked file | Track B: test widely | Arsha (from Nov 3) | not in the repo | 1 h | 1 | Ritik accepts its terms on Hugging Face and says so | blocked | not in the repo | task